## 통합
Master Status of Authors Supervision Card
Discipline | ASC No. | Revision | Unit | Building/ Item name | Part of Object | Title (Brief description) | Prochem/ Projomos |  |  | Licensor Engineer Signature |  |  | Owner |  |  |  |  | Owner Signature | REMARK
[7 empty] | Submitted Date | Received Date | Duration | Submitted Date | Received Date | Duration | Email No.(HEC) | Submitted Date | Email No.(Owner) | Received Date | Duration
건축 Only

## 토목
Master Status of Authors Supervision Card (CV)
Discipline | ASC No. | Revision | Unit | Building/ Item name | Part of Object | Title (Brief description) | Prochem/ Projomos |  |  | Licensor Engineer Signature |  |  | Owner |  |  |  |  | Owner Signature | REMARK
[7 empty] | Submitted Date | Received Date | Duration | Submitted Date | Received Date | Duration | Email No.(HEC) | Submitted Date | Email No.(Owner) | Received Date | Duration
건축 Only

## 건축
Master Status of Authors Supervision Card (AR)
Discipline | ASC No. | Revision | Unit | Building/ Item name | Part of Object | Title (Brief description) | Prochem/ Projomos |  |  | Licensor Engineer Signature |  |  | Owner |  |  |  |  | Owner Signature | REMARK
[7 empty] | Submitted Date | Received Date | Duration | Submitted Date | Received Date | Duration | Email No.(HEC) | Submitted Date | Email No.(Owner) | Received Date | Duration |  |  |  | Reply status
열1 | 열2 | 열3 | 열4 | 열5 | 열6 | 열7 | 열8 | 열9 | 열10 | 열11 | 열12 | 열13 | 열14 | 열15 | 열16 | 열17 | 열18 | 열19 | 열20 | 열21 | 열22
AR | HEC-PRCH-AR-0023 | 0 | Gen | Bitumen paint | - |  | Sent | Received | - |  |  |  | 00-HEC-PDHP-E-0557 | 2020-07-03 | 02-PDHP-HEC-E-1459 | 2021-11-03 | 488 | O |  |  | APV
AR | HEC-PRCH-AR-0014 | 1 | AUX3 | Remote Instrument Building(RIB-11) | Foundation |  | 2020.06.29 | 2020.06.30 | - |  |  |  | 00-HEC-PDHP-E-0567 | 2020-07-09 | 04-PDHP-HEC-E-0216 | 2020-12-01 | 145 | O
AR | HEC-PRCH-AR-0012 | 1 | PP | GPVI substation | Foundation Ground floor plan |  | 2020.08.05_수정본 제출 | 2020.08.24_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0671 | 2020-08-27 | 02-PDHP-HEC-E-0620 | 2020-10-07 | 41
AR | HEC-PRCH-AR-0012 | 1 | PP |  | Foundation Ground floor plan |  | - | - | - |  |  |  | 00-HEC-PDHP-E-0844 | 2020-10-09 | 02-PDHP-HEC-E-0640 | 2020-10-14 | 5 | O |  |  | W/ Comment by PMC)
AR | HEC-PRCH-AR-0020 | 0 | AUX2 | Fire water pump building | Foundation Ground floor plan |  | 2020.08.05_수정본 제출 | 2020.08.19_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0672 | 2020-08-27 | 04-PDHP-HEC-E-0187 | 2020-10-13 | 47 | O |  |  | W/ Comment (by PMC)
AR | HEC-PRCH-AR-0021 | 0 | PP | CYC gas compressor shelter-1 | Pile Foundaiton Ground floor |  | 2020.09.04 | 2020.09.16 | - |  |  |  | 00-HEC-PDHP-E-0734 | 2020-09-17 | 02-PDHP-HEC-E-0592 | 2020-09-25 | 8 | O |  |  | Approval
AR | HEC-PRCH-AR-0022 | 0 | PP | CYC gas compressor shelter-2 | Pile Foundaiton Ground floor |  | 2020.09.04 | 2020.09.16 | - |  |  |  | 00-HEC-PDHP-E-0735 | 2020-09-17 | 02-PDHP-HEC-E-0591 | 2020-09-25 | 8 | O |  |  | Approval
AR | HEC-PRCH-AR-0024 | 0 | PDH | Tail gas compressor shelter | Foundation |  | 2020.08.05_수정본 제출 | 2020.08.19_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0673 | 2020-08-27 | 01-PDHP-HEC-E-0240 | 2020-09-23 | 27 | O |  |  | W/ Comment
AR | HEC-PRCH-AR-0024 | 1 | PDH | - | Foundation |  | 2020.09.23 | 2020.09.24 | - |  |  |  | 00-HEC-PDHP-E-0764 | 2020-09-24 | 01-PDHP-HEC-E-0272 | 2020-09-12 |  | O | Updated is required as per agreed procedure |  | W/ Comment
AR | HEC-PRCH-AR-0024 | 1 | PDH | - | Foundation |  | - | - | - |  |  |  | - | - | 04-PDHP-HEC-E-0187 | 2020-10-13 | - |  |  |  | W/ Comment (by PMC)
AR | HEC-PRCH-AR-0025 | 0 | AUX2 | Phosphate injection & BFW package shelter | Foundation Equipment foundation Trench |  | 2020-08-05_수정본 제출 | 2020.08.24_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0674 | 2020-08-27 | 04-PDHP-HEC-E-0187 | 2020-10-13 | 47 | O |  |  | W/ Comment (by PMC)
AR | HEC-PRCH-AR-0026 | 0 | PP | T2 shelter | RC Part |  | 2020-08-05_수정본 제출 | 2020.08.24_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0675 | 2020-08-27 | 02-PDHP-HEC-E-0588 | 2020-09-25 | 29 | - | New version which is made like card for Prochem |  | W/ Comment
AR | HEC-PRCH-AR-0026 | 0 | PP | - | RC Part |  | - | - | - |  |  |  | 00-HEC-PDHP-E-0790 | 2020-09-29 | 02-PDHP-HEC-E-0605 | 2020-09-30 | 1 | O | Licensed Designer Stamp and Signature were already done |  | Approval
AR | HEC-PRCH-AR-0027 | 0 | PP | Vent recovery shelter | Pile Foundation |  | 2020-08-05_수정본 제출 | 2020.08.24_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0676 | 2020-08-27 | 02-PDHP-HEC-E-0587 | 2020-09-25 | 29 | - | New version which is made like card for Prochem |  | W/ Comment
AR | HEC-PRCH-AR-0027 | 1 | PP | - | Pile Foundation |  | 2020-09-29 | 2020.10.06 | - |  |  |  | 00-HEC-PDHP-E-0821 | 2020-10-07 | 02-PDHP-HEC-E-0628 | 2020-10-09 | 2 | O | Updated is required as per agreed procedure |  | W/ Comment
AR | HEC-PRCH-AR-0027 | 1 | PP | - | Pile Foundation |  | - | - | - |  |  |  | - | - | 02-PDHP-HEC-E-0645 | 2020-10-15 | - |  | Withdraw |  | W/ Comment
AR | HEC-PRCH-AR-0028 | 0 | PP | Pelletizing building | Foundation |  | 2020-08-08 | 2020.08.25_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0677 | 2020-08-27 | 02-PDHP-HEC-E-0586 | 2020-09-25 | 29 | - | Updated is required as per agreed procedure |  | W/ Comment
AR | HEC-PRCH-AR-0028 | 0 | PP | - |  |  | - | - | - |  |  |  | 00-HEC-PDHP-E-0791 | 2020-09-29 | 02-PDHP-HEC-E-0606 | 2020-09-30 | 1 | O | Related to Payment Milestone Card B 와 progress document/ Projmors 회신 완료 05-PDHP-HEC-E-0222 / Comment 접수/ 서명 도서는 비공식 email로 접수 됨 |  | Approval
AR | HEC-PRCH-AR-0029 | 0 | AUX1 | Dosing package shelter | Foundation Ground floor plan |  | 2020-08-05_수정본 제출 | 2020.08.19_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0678 | 2020-08-27 | 04-PDHP-HEC-E-0187 | 2020-10-13 | 47 | O |  |  | W/ Comment (by PMC)
AR | HEC-PRCH-AR-0030 | 0 | AUX1 | Spent caustic treatment package shelter | Foundation |  | 2020-08-05_수정본 제출 | 2020.08.19_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0679 | 2020-08-27 | 04-PDHP-HEC-E-0187 | 2020-10-13 | 47 | O | 0002와 2nb BP에 들어간 도면이 다른 경우 해당 도면들에 대해 Supervision card 작성 |  | W/ Comment (by PMC)
AR | HEC-PRCH-AR-0031 | 0 | AUX3 | WWT building | Foundation Ground Floor |  | 2020-08-05_수정본 제출 | 2020.08.24_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0680 | 2020-08-27 | 04-PDHP-HEC-E-0187 | 2020-10-13 | 47 | O | AWC 접수하였으므로 REVISION 하지 않을 예정 |  | W/ Comment (by PMC)
AR | HEC-PRCH-AR-0032 | 0 | AUX3 | Peroxide warehouse | Foundation Ground Floor Concrete Wall |  | 2020-08-05_수정본 제출 | 2020.08.19_prochem 승인 2020.09.16_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0681 | 2020-08-27 | 04-PDHP-HEC-E-0187 | 2020-10-13 | 47 | O |  |  | W/ Comment (by PMC)
AR | HEC-PRCH-AR-0032 | 1 | AUX3 |  | RC Part |  | 2021-07-01 | 2021-07-01 |  |  |  |  | 00-HEC-PDHP-E-1947 | 2021-07-07
AR | HEC-PRCH-AR-0034 | 0 | PP | Bitumen coating_Pelletizing building | Foundation only |  | 2020-08-19 | 2020.08.27_prochem 승인 2020.09.24_stamped KNA 접수 | - |  |  |  | 00-HEC-PDHP-E-0690 | 2020-09-01 | 02-PDHP-HEC-E-0589 | 2020-09-25 | 24 | - | 2021/08/24, 발주처/FE 협의에 따라 2nd BP 완료 후 ASC 수정/제출 예정 |  | W/ Comment
AR | HEC-PRCH-AR-0034 | 0 | PP | - |  |  | - | - | - |  |  |  | 00-HEC-PDHP-E-0792 | 2020-09-29 |  |  |  | O
AR | HEC-PRCH-AR-0033 | 0 | PP | Chemicals warehouse | RC Part Steel Part |  | 2020-08-28 | 2020-09-15 | 18 |  |  |  | 00-HEC-PDHP-E-0730 | 2020-09-17 | 02-PDHP-HEC-E-0622 | 2020-10-07 | 20 | O |  |  | AWC
AR | HEC-PRCH-AR-0035 | 0 | PP | PP unit substation | RC Part Steel Part |  | 2020-08-28 | 2020-09-15 | 18 |  |  |  | 00-HEC-PDHP-E-0724 | 2020-09-16 | 02-PDHP-HEC-E-0621 | 2020-10-07 | 21 | O |  |  | AWC
AR | HEC-PRCH-AR-0036 | 0 | AUX3 | Main substation | Foundation Ground floor 1st floor Framing elevation |  | 2020-08-28 | 2020-09-15 | 18 |  |  |  | 00-HEC-PDHP-E-0725 | 2020-09-22 | 04-PDHP-HEC-E-0216 | 2020-12-01 | 70 | O |  |  | AWC
AR | HEC-PRCH-AR-0037 | 0 | AUX2 | Utility substation | Foundation Ground floor 1st floor Framing elevation |  | 2020-08-28 | 2020-09-15 | 18 |  |  |  | 00-HEC-PDHP-E-0723 | 2020-09-16 | 04-PDHP-HEC-E-0251 | 2021-02-01 | 138 | O |  |  | Rejected
AR | HEC-PRCH-AR-0038 | 0 | AUX2 | Raw water Treatment shelter | Foundation Equipment foundation Ground Floor |  | 2020-09-09 | 2020-09-16 | 7 |  |  |  | 00-HEC-PDHP-E-0737 | 2020-09-17 | 04-PDHP-HEC-E-0187 | 2020-10-13 | 26 | - |  |  | W/ Comment (by PMC)
AR | HEC-PRCH-AR-0039 | 0 | PDH | Heat pump compressor shelter | RC Part |  | 2020-09-09 | 2020-09-16 | 7 |  |  |  | 00-HEC-PDHP-E-0733 | 2020-09-17 | 01-PDHP-HEC-E-0257 | 2020-10-12 | 25 | O |  |  | W/ Comment
AR | HEC-PRCH-AR-0040 | 0 | AUX2 | Demineralization package shelter | Foundation Equipment foundation Ground Floor |  | 2020-09-09 | 2020-09-25 | 16 |  |  |  | 00-HEC-PDHP-E-0842 | 2020-10-08 | 04-PDHP-HEC-E-0216 | 2020-12-01 | 54 | O |  |  | AWC
AR | HEC-PRCH-AR-0041 | 0 | PDH | Phosphate Injection Package Shelter(200-SHT-CC-700) | RC Part |  | 2020-09-16 | 2020-09-25 | 9 |  |  |  | 00-HEC-PDHP-E-0837 | 2020-10-08 | 01-PDHP-HEC-E-0279 | 2020-10-19 | 11 |  |  |  | Rejected
AR | HEC-PRCH-AR-0041 | 1 | PDH |  | RC Part |  | 2020-10-20 | 2020-10-21 | 1 |  |  |  | 00-HEC-PDHP-E-0879 | 2020-10-21 | 01-PDHP-HEC-E-0295 | 2020-10-27 | 6 | O |  |  | W/ Comment
AR | HEC-PRCH-AR-0042 | 0 | AUX3 | Remote Instrument Building(RIB-11) | Ground floor Roof |  | 2020-09-11 | 2020-09-25 | 14 |  |  |  | 00-HEC-PDHP-E-0836 | 2020-10-08 | 04-PDHP-HEC-E-0216 | 2020-12-01 | 54 | O |  |  | AWC
AR | HEC-PRCH-AR-0042 | 1 | AUX3 |  | Ground floor Roof |  | 2021-03-31 | 2021-04-19 | 19 |  |  |  | 00-HEC-PDHP-E-1618 | 2021-04-30 | 04-PDHP-HEC-E-0393 | 2021-05-19 | 19 | O |  |  | APV
AR | HEC-PRCH-AR-0043 | 0 | PDH | Chlorine Building(200-CH-31) | Foundation |  | 2020-09-11 | 2020-09-25 | 14 |  |  |  | 00-HEC-PDHP-E-0841 | 2020-10-08 | 01-PDHP-HEC-E-0280 | 2020-10-19 | 11 |  |  |  | Rejected
AR | HEC-PRCH-AR-0043 | 1 | PDH |  | Foundation |  | 2020-10-20 | 2020-10-28 | 8 |  |  |  | 00-HEC-PDHP-E-0896 | 2020-10-29 | 01-PDHP-HEC-E-0304 | 2020-11-04 | 6 | O
AR | HEC-PRCH-AR-0044 | 0 | PP | Pelletizing building | Pile Above structure(Concrete) |  | 2020-09-22 | 2020-09-28 | 6 |  |  |  | 00-HEC-PDHP-E-0840 | 2020-10-08 | 02-PDHP-HEC-E-0641 | 2020-10-14 | 6 | O |  |  | AWC (by PMC)
AR | HEC-PRCH-AR-0044 | 1 | PP |  | Pile Above structure(Concrete) Steel Structure |  | 2021-06-22 | 2021-06-29 | 7 |  |  |  | 00-HEC-PDHP-E-1946 | 2021-07-07 | 02-PDHP-HEC-E-1260 | 2021-07-20 | 13 | O |  |  | APV
AR | HEC-PRCH-AR-0045 | 0 | AUX2 | Utility substation | Foundation Ground floor 1st floor Framing elevation |  | 2020-09-17 | 2020-09-17 |  |  |  |  | 00-HEC-PDHP-E-0736 | 2020-09-17 | 04-PDHP-HEC-E-0216 | 2020-12-01 | 75 | O |  |  | AWC
AR | HEC-PRCH-AR-0046 | 0 | PDH | Net Gas Compressor Shelter(200-SHT-SH-300) | Pile Foundation Equipment foundation(UG Part) |  | 2020-09-16 | 2020-09-25 | 9 |  |  |  | 00-HEC-PDHP-E-0839 | 2020-10-08 | 01-PDHP-HEC-E-0281 | 2020-10-15 | 7
AR | HEC-PRCH-AR-0046 | 1 | PDH |  | Pile RC Part |  | 2020-11-03 | 2020-11-05 | 2 |  |  |  | 00-HEC-PDHP-E-0966 | 2020-11-11 | 01-PDHP-HEC-E-0327 | 2020-11-23 | 12 | O
AR | HEC-PRCH-AR-0047 | 0 | PP | GPVI substation | 1st Floor Roof Floor Roof Steel Structure |  | 2020-09-22 | 2020-09-28 | 6 |  |  |  | 00-HEC-PDHP-E-0789 | 2020-09-29 | 02-PDHP-HEC-E-0739 | 2020-12-01 | 63 | O |  |  | AWC
AR | HEC-PRCH-AR-0048 | 0 | PDH | Reactor Effluent Compressor Shelter(200-SHT-SH-100) | Pile Foundation Equipment Foundation Ground Floor |  | 2020-09-29 | 2020-10-06 | 7 |  |  |  | 00-HEC-PDHP-E-0838 | 2020-10-08 | 01-PDHP-HEC-E-0282 | 2020-10-15 | 7 | O |  |  | AWC
AR | HEC-PRCH-AR-0049 | 0 | PDH | Refrigeration Equipment Shelter(200-SHT-CO-500) | Foundation Equipment Foundation Ground Floor |  | 2020-09-29 | 2020-10-06 | 7 |  |  |  | 00-HEC-PDHP-E-0835 | 2020-10-08 | 01-PDHP-HEC-E-0283 | 2020-10-15 | 7 | O
AR | HEC-PRCH-AR-0049 | 1 | PDH |  | RC Part Steel Part Micro Pile |  | 2021-03-10 | 2021-03-11 | 1 |  |  |  | 00-HEC-PDHP-E-1404 | 2021-03-19 | 01-PDHP-HEC-E-0440 | 2021-04-01 | 13 | O |  |  | APV
AR | HEC-PRCH-AR-0050 | 0 | GEN | Environmental Corrosive Category | -
AR | HEC-PRCH-AR-0051 | 0 | AUX2 | Fire Water Pump Building(810-SHT-SC-300) | Foundation Ground Floor Equipment Foundation Roof Above Steel Structure |  | 2020-10-06 | 2020-10-09 | 3 |  |  |  | 00-HEC-PDHP-E-0857 | 2020-10-15 | 04-PDHP-HEC-E-0251 | 2021-02-01 | 109 | O |  |  | AWC
AR | HEC-PRCH-AR-0052 | 0 | AUX3 | Air Compressor & Air Dryer Package Shelter (830-SHT-CH-100) | Foundation Equipment Foundation Ground Floor |  | 2020-10-06 | 2020-10-12 | 6 |  |  |  | 00-HEC-PDHP-E-0856 | 2020-10-15 | 04-PDHP-HEC-E-0216 | 2020-12-1 | 47 | O |  |  | AWC
AR | HEC-PRCH-AR-0052 | 1 | AUX3 |  | RC Part Steel Part |  | 2021-07-27 | 2021-07-29 | 2 |  |  |  | 00-HEC-PDHP-E-2116 | 2021-08-10 | 04-PDHP-HEC-E-0560 | 2021-08-20 | 10 |  |  |  | APV
AR | HEC-PRCH-AR-0053 | 0 | PDH | Tail Gas Compressor Shelter(200-SHT-CO-400) | Ground slab Steel frame |  | 2020-10-16 | 2020-10-16 |  |  |  |  | 00-HEC-PDHP-E-0904 | 2020-10-30 | 01-PDHP-HEC-E-0306 | 2020-11-05 | 6 | O |  |  | AWC
AR | HEC-PRCH-AR-0054 | 0 | PP | Vent Recovery Compressor Shelter(300-SHT-SH-600) | Ground slab Steel frame |  | 2020-10-16 | 2020-10-16 |  |  |  |  | 00-HEC-PDHP-E-0905 | 2020-10-30 | 02-PDHP-HEC-E-0688 | 2020-11-06 | 7 | O |  |  | AWC
AR | HEC-PRCH-AR-0054 | 1 | PP |  | Ground slab Steel frame |  | 2021-06-24 | 2021-07-01 | 7 |  |  |  | 00-HEC-PDHP-E-1944 | 2021-07-07 | 02-PDHP-HEC-E-1257 | 2021-07-20 | 13 | O |  |  | APV
AR | HEC-PRCH-AR-0055 | 0 | PDH,PP | DSM locaion plan(PDH, PP) | DSM locaiton plan |  | 2020-10-12 | 2020-10-20 | 8 |  |  |  | 00-HEC-PDHP-E-0878 | 2020-10-21 | 02-PDHP-HEC-E-0673 | 2020-11-03 | 13 | O
AR | HEC-PRCH-AR-0056 | 0 | PDH | Chlorine Building(200-CH-31) | Ground floor Roof |  | 2020-10-16 | 2020-10-21 | 5 |  |  |  | 00-HEC-PDHP-E-0906 | 2020-10-30 | 01-PDHP-HEC-E-0307 | 2020-11-05 | 6 | O
AR | HEC-PRCH-AR-0057 | 0 | AUX2 | Phosphate Injection & BFW Treatment Package Shelter(820-SHT-CC-200) | RC Part Steel Part |  | 2020-10-16 | 2020-10-21 | 5 |  |  |  | 00-HEC-PDHP-E-0907 | 2020-10-30 | 04-PDHP-HEC-E-0251 | 2021-02-01 | 94 | O |  |  | APV
AR | HEC-PRCH-AR-0058 | 0 | AUX1 | Side Stream Filters Package Shelter(860-SHT-CC-200) | RC Part Steel Part |  | 2020-10-19 | 2020-10-22 | 3 |  |  |  | 00-HEC-PDHP-E-0908 | 2020-10-30 | 04-PDHP-HEC-E-0251 | 2021-02-01 | 94 | O |  |  | AWC
AR | HEC-PRCH-AR-0059 | 0 | AUX1 | Dosing Package Shelter(860-SHT-CC-100) | RC Part Steel Part |  | 2020-10-19 | 2020-10-22 | 3 |  |  |  | 00-HEC-PDHP-E-0909 | 2020-10-30 | 04-PDHP-HEC-E-0251 | 2021-02-01 | 94 | O |  |  | AWC
AR | HEC-PRCH-AR-0060 | 0 | PDH | Chlorination System Shelter(200-SHT-CC-600) | RC Part Steel Part |  | 2020-10-23 | 2020-10-29 | 6 |  |  |  | 00-HEC-PDHP-E-0967 | 2020-11-11 | 01-PDHP-HEC-E-0322 | 2020-11-20 | 9 | O
AR | HEC-PRCH-AR-0061 | 0 | AUX3 | Spent Caustic Treatment Package Shelter(850-SHT-CH-200) | Ground Slab Steel Part |  | 2020-10-23 | 2020-10-28 | 5 |  |  |  | 00-HEC-PDHP-E-0910 | 2020-10-30 | 04-PDHP-HEC-E-0251 | 2021-02-01 | 94 | O |  |  | AWC
AR | HEC-PRCH-AR-0062 | 0 | AUX3 | Turbine Expander Shelter(830-SHT-CH-200) | Ground Slab Steel Part |  | 2020-10-23 | 2020-10-28 | 5 |  |  |  | 00-HEC-PDHP-E-0902 | 2020-10-30 | 04-PDHP-HEC-E-0251 | 2021-02-01 | 94 | O |  |  | AWC
AR | HEC-PRCH-AR-0063 | 0 | PPL | Silo Building | Foundation |  | 2020-10-23 | 2020-10-28 | 5 |  |  |  | 00-HEC-PDHP-E-0897 | 2020-10-29 | 03-PDHP-HEC-E-0232 | 2020-11-05 | 7 | O
AR | HEC-PRCH-AR-0064 | 0 | PPL | Packaging Hall - Administrative-Social Building | Foundation Steel Roof |  | 2020-10-23 | 2020-10-28 | 5 |  |  |  | 00-HEC-PDHP-E-0898 | 2020-10-29 | 03-PDHP-HEC-E-0228 | 2020-10-30 | 1
AR | HEC-PRCH-AR-0064 | 0 | PPL |  | Foundation Steel Roof |  | - | - | - |  |  |  | 00-HEC-PDHP-E-0929 | 2020-11-05 | 03-PDHP-HEC-E-0237 | 2020-11-17 | 12 | O
AR | HEC-PRCH-AR-0065 | 0 | PP | Nitrogen, Ethylene & Hydrogen Compressor Shelter(300-SHT-SH-200) | RC Part Steel Part |  | 2020-11-02 | 2020-11-05 | 3 |  |  |  | 00-HEC-PDHP-E-0993 | 2020-11-27 | 02-PDHP-HEC-E-0763 | 2020-12-11 | 14 | O |  |  | APV
AR | HEC-PRCH-AR-0065 | 1 | PP |  | RC Part Steel Part |  | 2021-06-21 | 2021-07-01 | 10 |  |  |  | 00-HEC-PDHP-E-1945 | 2021-07-07 | 02-PDHP-HEC-E-1256 | 2021-07-20 | 13 | O |  |  | APV
AR | HEC-PRCH-AR-0066 | 0 | PP | Analyzer House | RC Part |  | 2020-11-02 | 2020-11-16 | 14 |  |  |  | 00-HEC-PDHP-E-0989 | 2020-11-26 | 02-PDHP-HEC-E-0764 | 2020-12-11 | 15 | O |  |  | APV
AR | HEC-PRCH-AR-0067 | 0 | AUX3 | Main substation(1000-SS-01) | Arch. Part |  | 2020-10-30 | 2020-11-05 | 6 |  |  |  | 00-HEC-PDHP-E-0999 | 2020-11-30 | 04-PDHP-HEC-E-0251 | 2021-02-01 | 63 | O |  |  | AWC
AR | HEC-PRCH-AR-0068 | 0 | PP | GPVI substation(1000-SS-05) | Arch. Part |  | 2020-11-02 | 2020-11-30 | 28 |  |  |  | 00-HEC-PDHP-E-1063 | 2020-12-17 | 02-PDHP-HEC-E-0805 | 2021-01-07 | 21 | O |  |  | AWC
AR | HEC-PRCH-AR-0068 | 1 | PP |  | Arch. Part |  | 2021-05-31 | 2021-06-29 | 29 |  |  |  | 00-HEC-PDHP-E-1922 | 2021-07-01
AR | HEC-PRCH-AR-0069 | 0 | AUX2 | Steam turbine generator shelter(820-SHT-SH-300) | RC Part Steel Part |  | 2020-12-04 | 2020-12-08 | 4 |  |  |  | 00-HEC-PDHP-E-1039 | 2020-12-09 | 04-PDHP-HEC-E-0227 | 2020-12-18 | 9 | O |  |  | APV
AR | HEC-PRCH-AR-0069 | 1 | AUX2 |  | RC Part Steel Part Micro Pile |  | 2021-02-24 | 2021-03-08 | 12 |  |  |  | 00-HEC-PDHP-E-1403 | 2021-03-19 | 04-PDHP-HEC-E-0306 | 2021-03-22 | 3 | O |  |  | APV
AR | HEC-PRCH-AR-0070 | 0 | AUX3 | Propyele vapours compressor shelter(610-SHT-SO-200) | RC Part Steel Part |  | 2020-12-01 | 2021-02-15 | 76 |  |  |  | 00-HEC-PDHP-E-1250 | 2021-02-19 | 04-PDHP-HEC-E-0958 | 2022-07-14 | 510 | O |  |  | AWC
AR | HEC-PRCH-AR-0071 | 0 | GEN | Remove lean concrete for S.O.G. for open shelter | Lean concrete |  | 2020-12-30 | 2021-01-04 | 5 |  |  |  | 00-HEC-PDHP-E-1086 | 2021-01-05 | 04-PDHP-HEC-E-0266 | 2021-02-11 | 37 | O |  |  | Rejected
AR | HEC-PRCH-AR-0072 | 0 | PDH, PP, AUX3, AUX1 | Operator shelter(1000-OB-45ABCD) | RC part |  | 2021-05-14 | 2021-06-01 | 18 |  |  |  | 00-HEC-PDHP-E-2398 | 2021-10-13
AR | HEC-PRCH-AR-0073 | 0 | PP | PP unit substation(1000-SS-03) | Arch. Part |  | 2020-12-17 | 2020-12-22 | 5 |  |  |  | 00-HEC-PDHP-E-1090 | 2021-01-07 | 02-PDHP-HEC-E-0831 | 2021-01-19 | 12 | X |  |  | Rejected
AR | HEC-PRCH-AR-0073 | 0 | PP |  | - |  | - | - | - |  |  |  | 00-HEC-PDHP-E-1169 | 2021-02-02 | 02-PDHP-HEC-E-0900 | 2021-02-22 | 20 | X |  |  | Rejected
AR | HEC-PRCH-AR-0073 | 1 | PP | [9 empty] | 00-HEC-PDHP-E-1587 | 2021-04-28 | 02-PDHP-HEC-E-1098 | 2021-05-11 | 13 | O |  |  | APV
AR | HEC-PRCH-AR-0074 | 0 | AUX2 | Utility substation(1000-SS-01) | Arch. Part |  | 2020-12-22 | 2021-01-11 | 20 |  |  |  | 00-HEC-PDHP-E-1174 | 2021-02-03 | 04-PDHP-HEC-E-0478 | 2021-07-09 | 156 | O |  |  | APV
AR | HEC-PRCH-AR-0075 | 0 | AUX2 | Raw water Treatment Building | Steel Part |  | 2021-04-13 | 2021-04-16 | 3 |  |  |  | 00-HEC-PDHP-E-1617 | 2021-04-30 | 04-PDHP-HEC-E-0387 | 2021-05-18 | 18 | O |  |  | APV
AR | HEC-PRCH-AR-0076 | 0 | PP | CYC gas compressor shelter-2 | Steel Part |  | 2021-03-12 | 2021-03-16 | 4 |  |  |  | 00-HEC-PDHP-E-1397 | 2021-03-18 | 02-PDHP-HEC-E-0989 | 2021-03-25 | 7 | O |  |  | APV
AR | HEC-PRCH-AR-0077 | 0 | PP | CYC gas compressor shelter-1 | Steel Part |  | 2021-03-31 | 2021-04-09 | 9 |  |  |  | 00-HEC-PDHP-E-1568 | 2021-04-23 | 02-PDHP-HEC-E-1123 | 2021-05-19 | 26 | O |  |  | APV
AR | HEC-PRCH-AR-0078 | 0 | AUX6 | Air Intake Station(1000-AI-43) | RC Part Steel Part |  | 2021-04-13 | 2021-04-16 | 3 |  |  |  | 00-HEC-PDHP-E-1625 | 2021-05-01 | 04-PDHP-HEC-E-0371 | 2021-05-10 | 9 | O |  |  | APV
AR | HEC-PRCH-AR-0079 | 0 | AUX6 | Air Intake Station(1000-AI-43) | Arch. Part |  | 2021-04-13 | 2021-04-21 | 8 |  |  |  | 00-HEC-PDHP-E-1586 | 2021-04-28 | 04-PDHP-HEC-E-0385 | 2021-05-18 | 20 |  |  |  | APV
AR | HEC-PRCH-AR-0079 | 1 | AUX6 |  | Arch. Part |  | 2021-05-28 | 2021-06-07 | 10 |  |  |  | 00-HEC-PDHP-E-1829 | 2021-06-16 | 04-PDHP-HEC-E-0461 | 2021-06-29 | 13 | O |  |  | APV
AR | HEC-PRCH-AR-0080 | 0 | AUX3 | 600-P0001A/B Foundation | RC part |  | 2021-04-26 | 2021-04-27 | 1 |  |  |  | 00-HEC-PDHP-E-1627 | 2021-05-03 | 04-PDHP-HEC-E-0372 | 2021-05-12 | 9 | O |  |  | APV
AR | HEC-PRCH-AR-0081 | 0 | AUX3 | 600-P0003A/B Foundation | RC part |  | 2021-04-26 | 2021-04-27 | 1 |  |  |  | 00-HEC-PDHP-E-1630 | 2021-05-03 | 04-PDHP-HEC-E-0405 | 2021-05-21 | 18 | O |  |  | APV
AR | HEC-PRCH-AR-0082 | 0 | AUX2 | 820-P0002A/B Foundation | RC part |  | 2021-04-26 | 2021-04-28 | 2 |  |  |  | 00-HEC-PDHP-E-1631 | 2021-05-03 | 04-PDHP-HEC-E-0406 | 2021-05-21 | 18 | O |  |  | APV
AR | HEC-PRCH-AR-0083 | 0 | AUX3 | PROPYLENE LOADING ARM SHELTER(610-SHT-SO-100) | RC Part Steel Part |  | 2021-05-14 | 2021-06-16 | 33 |  |  |  | 00-HEC-PDHP-E-1840 | 2021-06-18 | 04-PDHP-HEC-E-0459 | 2021-06-29 | 11 |  |  |  | Rejected
AR | HEC-PRCH-AR-0083 | 1 | AUX3 |  | RC Part Steel Part |  | 2021-07-01 | 2021-07-01 |  |  |  |  | 00-HEC-PDHP-E-1938 | 2021-07-07
AR | HEC-PRCH-AR-0084 | 0 | PP | Nitrogen, Ethylene & Hydrogen Compressor Shelter(300-SHT-SH-200) | Arch. Part |  | 2021-05-31 | 2021-06-16 | 16 |  |  |  | 00-HEC-PDHP-E-1950 | 2021-07-07 | 02-PDHP-HEC-E-1259 | 2021-07-20 | 13 | O |  |  | AWC
AR | HEC-PRCH-AR-0086 | 0 | PP | CYC gas compressor shelter-2 | Arch. Part |  | 2021-06-03 | 2021-06-09 | 6 |  |  |  | 00-HEC-PDHP-E-1951 | 2021-07-07 | 02-PDHP-HEC-E-1261 | 2021-07-20 | 13 | X |  |  | REJ
AR | HEC-PRCH-AR-0087 | 0 | PP | Vent Recovery Compressor Shelter(300-SHT-SH-600) | Arch. Part |  | 2021-06-10 | 2021-06-16 | 6 |  |  |  | 00-HEC-PDHP-E-1949 | 2021-07-07 | 02-PDHP-HEC-E-1258 | 2021-07-20 | 13 | O |  |  | AWC
AR | HEC-PRCH-AR-0088 | 0 | PP | T2 shelter | Steel Part |  | 2021-06-10 | 2021-06-23 | 13 |  |  |  | 00-HEC-PDHP-E-1914 | 2021-06-30 | 02-PDHP-HEC-E-1253 | 2021-07-20 | 20 | O |  |  | APV
AR | HEC-PRCH-AR-0089 | 0 | GEN | Changed Roofing System for RC Building | - |  | 2021-06-10 | 2021-06-25 | 15 |  |  |  | 00-HEC-PDHP-E-1893 | 2021-06-29
AR | HEC-PRCH-AR-0090 | 0 | PP | T2 shelter | Arch. Part |  | 2021-06-10 | 2021-06-16 | 6 |  |  |  | 00-HEC-PDHP-E-2446 | 2021-10-13 | 02-PDHP-HEC-E-1453 | 2021-11-02 | 20 | O |  |  | APV
AR | HEC-PRCH-AR-0092 | 0 | AUX4 | Storage Building(1000-ST-34) | RC/Steel Part |  | 2021-06-10 | 2021-06-23 | 13 |  |  |  | 00-HEC-PDHP-E-1913 | 2021-06-30
AR | HEC-PRCH-AR-0093 | 0 | PP | Chemicals warehouse | Arch. Part |  | 2021-06-16 | 2021-06-23 | 7 |  |  |  | 00-HEC-PDHP-E-1923 | 2021-07-01 | 02-PDHP-HEC-E-1255 | 2021-07-20 | 19 | O |  |  | APV
AR | HEC-PRCH-AR-0094 | 0 | AUX4 | Laboratory Building | Arch. Part |  | 2021-07-05 | 2021-07-07 | 2 |  |  |  | 00-HEC-PDHP-E-2446 | 2021-10-13 | 04-PDHP-HEC-E-0655 | 2021-11-04 | 22 | X |  |  | REJ
AR | HEC-PRCH-AR-0094 | 1 | AUX4 | Laboratory Building | Arch. Part |  | 2021-11-09 | 2021-11-16 | 7 |  |  |  | 00-HEC-PDHP-E-2823 | 2021-12-31 | 04-PDHP-HEC-E-0749 | 2022-02-16 | 47 | X |  |  | AWC
AR | HEC-PRCH-AR-0094 | 1 | AUX4 | Laboratory Building | Arch. Part | [7 empty] | 04-HEC-PDHP-E-1155 | 2022-10-13 | 04-PDHP-HEC-E-1140 | 2022-10-19 | 6 | O | CS 답변 작성 |  | APV
AR | HEC-PRCH-AR-0095 | 0 | AUX4 | Guard House (Aux) | Arch. Part |  | 2021-07-01 | 2021-07-01 |  |  |  |  | 00-HEC-PDHP-E-2481 | 2021-10-15 | 04-PDHP-HEC-E-0656 | 2021-11-05 | 21 | O |  |  | APV
AR | HEC-PRCH-AR-0096 | 0 | AUX4 | Guard House (Aux) | RC. Part |  | 2021-06-25 | 2021-07-06 | 11 |  |  |  | 00-HEC-PDHP-E-2010 | 2021-07-21 | 04-PDHP-HEC-E-0548 | 2021-08-17 | 27 | O |  |  | APV
AR | HEC-PRCH-AR-0097 | 0 | PDH | Chlorination System Shelter(200-SHT-CC-600) | Arch. Part |  | 2021-06-28 | 2021-07-08 | 10 |  |  |  | 00-HEC-PDHP-E-2500 | 2021-10-20
AR | HEC-PRCH-AR-0098 | 0 | PDH | Chlorination System Shelter(200-SHT-CC-600) | RC, Steel Part |  | 2021-06-25 | 2021-06-25 |  |  |  |  | 00-HEC-PDHP-E-1912 | 2021-06-30 | 01-PDHP-HEC-E-0576 | 2021-07-14 | 14 | O |  |  | APV
AR | HEC-PRCH-AR-0099 | 0 | PDH | Deluge Valve Shelter (PDH No.1~No.5) | Arch. Part |  | 2021-07-01 | 2021-07-12 | 11
AR | HEC-PRCH-AR-0100 | 0 | PDH | Deluge Valve Shelter (PDH No.1~No.5) | RC |  | 2021-07-01 | 2021-07-12 | 11 |  |  |  | 00-HEC-PDHP-E-2011 | 2021-07-21 | 01-PDHP-HEC-E-0613 | 2021-08-03 | 13 | X |  |  | REJ
AR | HEC-PRCH-AR-0100 | 1 | PDH |  | RC |  | 2021-07-27 | 2021-07-29 | 2 |  |  |  | 00-HEC-PDHP-E-2107 | 2021-08-09
AR | HEC-PRCH-AR-0101 | 0 | PPL | 01 Administrative Building, Packing hall, Silo | Arch. Part |  | 2021-08-05 | 2021-08-13 | 8 |  |  |  | 00-HEC-PDHP-E-2389 | 2021-10-08 | 03-PDHP-HEC-E-0472 | 2021-10-12 | 4 | O |  |  | APV
AR | HEC-PRCH-AR-0102 | 0 |  | 01 Administrative Building | RC Part | [7 empty] | Canceled
AR | HEC-PRCH-AR-0103 | 0 |  | 02 Building of Packing Hall | Arch. Part | [7 empty] | Canceled
AR | HEC-PRCH-AR-0104 | 0 |  | 02 Building of Packing Hall | RC / Steel Part | [7 empty] | Canceled
AR | HEC-PRCH-AR-0105 | 0 |  | 03 Silo Building | Arch. Part | [7 empty] | Canceled
AR | HEC-PRCH-AR-0106 | 0 |  | 03 Silo Building | RC / Steel Part | [7 empty] | Canceled
AR | HEC-PRCH-AR-0107 | 0 | PPL | 04 GUARD HOUSE / 05 CANOPY | Arch. Part |  | 2021-08-04 | 2021-08-13 | 9 |  |  |  | 00-HEC-PDHP-E-2327 | 2021-09-28 | - | - | - | - | IFC Signed DWG의 ASC No. 수정하여 재 제출함 (발주처/FE 협의 완료)
AR | HEC-PRCH-AR-0107 | 0 | PPL |  | Arch. Part | [7 empty] | 00-HEC-PDHP-E-2431 | 2021-10-08 | 03-PDHP-HEC-E-0475 | 2021-10-14 | 6 | O |  |  | APV
AR | HEC-PRCH-AR-0108 | 0 | PPL | 04 GUARD HOUSE / 05 CANOPY | RC / Steel Part |  | 2021-08-04 | 2021-08-12 | 8 |  |  |  | 00-HEC-PDHP-E-2309 | 2021-09-10 | 02-PDHP-HEC-E-1378 | 2021-10-01 | 21 | X |  |  | REJ
AR | HEC-PRCH-AR-0108 |  | PPL | [9 empty] | 02-HEC-PDHP-E-1009 | 2021-09-30 | 03-PDHP-HEC-E-0471 | 2021-10-12 | 12 | O |  |  | APV
AR | HEC-PRCH-AR-0109 | 0 | PDH | Net Gas Compressor Shelter(200-SHT-SH-300) | Arch. Part |  | 2021-07-05 | 2021-07-06 | 1
AR | HEC-PRCH-AR-0110 | 0 | PDH | Net Gas Compressor Shelter(200-SHT-SH-300) | RC / Steel Part |  | 2021-07-05 | 2021-07-07 | 2 |  |  |  | 00-HEC-PDHP-E-2012 | 2021-07-21 | 01-PDHP-HEC-E-0614 | 2021-08-03 | 13 | X |  |  | REJ
AR | HEC-PRCH-AR-0110 | 1 | PDH |  | RC / Steel Part |  | 2021-07-27 | 2021-07-29 | 2 |  |  |  | 00-HEC-PDHP-E-2108 | 2021-08-09 | 01-PDHP-HEC-E-0925 | 2022-05-25 | 289 | O |  |  | APV
AR | HEC-PRCH-AR-0111 | 0 | AUX4 | CENTRAL CONTROL BUILDING(1000-CCR-21) | Arch. Part |  | 2021-07-16 | 2021-07-16
AR | HEC-PRCH-AR-0112 | 0 | AUX3 | Deluge Valve Shelter (AUX No.1) | New Object |  | 2021-07-23 | 2021-08-03 | 11 |  |  |  | 00-HEC-PDHP-E-2143 | 2021-08-13 | 04-PDHP-HEC-E-0557 | 2021-08-23 | 10 | X |  |  | REJ
AR | HEC-PRCH-AR-0112 | 1 | AUX3 | [9 empty] | 00-HEC-PDHP-E-2643 | 2021-11-24 | 04-PDHP-HEC-E-0670 | 2021-12-06 | 12 | O |  |  | APV
AR | HEC-PRCH-AR-0113 | 0 | AUX1 | Deluge Valve Shelter (AUX No.3) | New Object |  | 2021-07-23 | 2021-07-29 | 6 |  |  |  | 00-HEC-PDHP-E-2144 | 2021-08-13 | 04-PDHP-HEC-E-0557 | 2021-08-23 | 10 | X |  |  | REJ
AR | HEC-PRCH-AR-0113 | 1 | AUX1 | [9 empty] | 00-HEC-PDHP-E-2644 | 2021-11-24 | 04-PDHP-HEC-E-0669 | 2021-12-06 | 12 | X |  |  | REJ
| HEC-PRCH-AR-0113 | 1 | AUX1 | [9 empty] | 00-HEC-PDHP-E-2826 | 2021-12-31
AR | HEC-PRCH-AR-0114 | 0 | PP | CYC gas compressor shelter-2 | Arch. Part |  | 2021-07-23 | 2021-07-29 | 6 | [9 empty] | Signed IFC 미접수로 ASC 제출 대기중
AR | HEC-PRCH-AR-0115 | 0 | PP | Deluge Valve Shelter(PP No.1/2/3) | New Object |  | 2021-07-29 | 2021-09-07 | 40 |  |  |  | 00-HEC-PDHP-E-2491 | 2021-10-19 | 02-PDHP-HEC-E-1453 | 2021-11-02 | 14 | O |  |  | APV
AR | HEC-PRCH-AR-0116 | 0 | PP | Charging Station(300-SHT-SH-800) | New Object |  | 2022-03-11 | 2022-03-15 | 4 |  |  |  | 00-HEC-PDHP-E-3184 | 2022-03-24 | 02-PDHP-HEC-E-1729 | 2022-04-05 | 12 | O | 추후 수정시 첨부파일은 plot plan말고 BP포함된 SDP사용으로 수정 |  | AWC
AR | HEC-PRCH-AR-0117 | 0 | AUX1, AUX2, AUX3 | Sandwich panel | Heat transfer coefficient |  | 2022-05-18 | 2022-05-25 | 7 |  |  |  | 00-HEC-PDHP-E-3469 | 2022-05-28
AR | HEC-PRCH-AR-0118 | 0 | AUX3 | Main substation(1000-SS-01) | Cable celler room insulatoin |  | 2022-05-27 | 2022-05-30 | 3 |  |  |  | 00-HEC-PDHP-E-3476 | 2022-05-31
AR | HEC-PRCH-AR-0119 | 0 | AUX3 | Main substation(1000-SS-01) | Internal fire rated wall | Remove fire resistant class from BP drawing | 2022-06-20 | 2022-07-18 | 28 |  |  |  | 00-HEC-PDHP-E-3640 | 2022-07-21
AR | HEC-PRCH-AR-0120 | 0 | AUX3 | Green Area (AUX 3) | Green area | reduce green area | 2022-07-19 | 2022-07-20 | 1 |  |  |  | 00-HEC-PDHP-E-3645 | 2022-07-25
AR | HEC-PRCH-AR-0121 | 0 | AUX4 | Laboratory Building(1000-LB-41) | Internal fire rated wall | Remove fire resistant class from BP drawing
AR | HEC-PRCH-AR-0122 | 0 | AUX4 | 3C area building | Firefighting zone | Rearrange firefighting zone | 2022-09-16 | 2022-10-26 | 40 |  |  |  | 00-HEC-PDHP-E-4046 | 2022-12-03 | 04-PDHP-HEC-E-139 | 2023-01-23 | 51 | O |  |  | APV
AR | HEC-PRCH-AR-0123 | 0 | AUX2 | Fire water pump building | fire resistant class of window |  | 2023-02-14 | 2023-02-27 | 13 |  |  |  | 00-HEC-PDHP-E-4378 | 2023-04-18
AR | HEC-PRCH-AR-0124 | 0 | PP | Pelletizing building | Fire resistant door on stair |  | 2023-03-07 | 2023-03-09 | 2 |  |  |  | 00-HEC-PDHP-E-4379 | 2023-04-18
AR | HEC-PRCH-AR-0125 | 0 | AUX2 | Fire water pump building | Door size change |  | 2023-04-26 | 2023-04-27 | 1 |  |  |  | 00-HEC-PDHP-E-4438 | 2023-05-15
| HEC-PRCH-AR-0126 | 0
| HEC-PRCH-AR-0127 | 0 | AUX4 | CENTRAL CONTROL BUILDING(1000-CCR-21) | Ramp for disabled people |  | 2023-10-05 | 2023-10-06 | 1
| HEC-PRCH-AR-0128 | 0 | PP | GPVI substation | Fire separation |  | 2023-10-20 | [5 empty] | 00-HEC-PDHP-E-4730 | 2023-11-09
AR | HEC-PRCH-AR-0129 | 0 | AUX4 | 3C area building | Fire door | change the fire resistant class of the doors
AR | HEC-PRCH-AR-0130 | 0 | AUX2 | STEAM TURBINE SHELTER | Platform 수정 | [7 empty] | 00-HEC-PDHP-E-4906 | 2024-02-13
AR | HEC-PROJ-AR-0001 | 0 |  | Terminal control room building | All part of building |  | 2020-07-18 | [5 empty] | Canceled | [5 empty] | Deleted
AR | HEC-PROJ-AR-0001 | 0 | [16 empty] | Deleted
AR | HEC-PROJ-AR-0002 | 0 |  | Transformer station | All part of building |  | 2020-07-18 | [5 empty] | Canceled | [5 empty] | Deleted
AR | HEC-PROJ-AR-0002 | 0 |  |  | All part of building |  | 2020-11-03 | 2021-03-30 | 147 | [9 empty] | Deleted
AR | HEC-PROJ-AR-0003 | 0 |  | BOG compressor shelter | Pile RC Part Steel Structre |  | 2020-09-22 | [5 empty] | Canceled | [5 empty] | Deleted
AR | HEC-PROJ-AR-0003 | 0 |  |  | Pile RC Part Steel Structre |  | 2020-11-10 | 2021-03-30 | 140 | [9 empty] | Deleted
AR | HEC-PROJ-AR-0004 | 0 |  | Fire and Process Water Pump Station(100-SHT-SC-300) | Pile Foundation Ground Floor |  | 2020-09-30 | 2020-11-06 | 37 |  |  |  | Canceled | [5 empty] | Deleted
AR | HEC-PROJ-AR-0005 | 0 |  | Control Station(1000-GH-45) | Pile Foundation Ground Floor Roof | [7 empty] | Canceled | [5 empty] | Deleted
AR | HEC-PROJ-AR-0006 | 0 |  | Guard House-HST(100-GH-46) | Pile Foundation Ground Floor Roof |  | 2020-09-30 | 2021-03-30 | 181 |  |  |  | Canceled | [5 empty] | Deleted
AR | HEC-PROJ-AR-0007 | 0 | HST | Pile Location Plan | Pile |  | 2020-11-10 | 2020-11-23 2021-03-30 | - |  |  |  | 05-HEC-PDHP-E-0230 | 2020-11-26 | Unofficial | 2020-12-31 | 35 | O |  |  | AWC
AR | HEC-PROJ-AR-0008 |  |  | Terminal control room building | Structural drawing. |  | 2020-12-04 | 2021-03-30 | 116 |  |  |  | Canceled | [5 empty] | Deleted
AR | HEC-PROJ-AR-0009 |  |  | Transformer station | AR part Structural drawing | [7 empty] | Canceled | [5 empty] | Deleted
AR | HEC-PROJ-AR-0010 | 0 | HST | Changed Roofing System for RC Building | - |  | 2021-06-18 | 2021-06-30 | 12 |  |  |  | 00-HEC-PDHP-E-1907 | 2021-06-30 | 05-PDHP-HEC-E-0440 | 2021-07-09 | 9 | X |  |  | AWC
AR | HEC-PROJ-AR-0010 | 0 | HST | [9 empty] | 05-HEC-PDHP-E-0642 | 2021-09-16 | 05-PDHP-HEC-E-0528 | 2021-09-24 | 8 | X |  |  | AWC
AR | HEC-PROJ-AR-0010 | 1 | HST | [9 empty] | 00-HEC-PDHP-E-2580 | 2021-11-05 | 05-PDHP-HEC-E-0566 | 2021-11-12 | 7 | X |  |  | AWC
AR | HEC-PROJ-AR-0010 | 1 | HST | [9 empty] | 05-HEC-PDHP-E-0771 | 2022-01-05 | 05-PDHP-HEC-E-0617 | 2022-01-15 | 10 | X |  |  | AWC
[13 empty] | 05-HEC-PDHP-E-1177 | 2022-10-14 | 05-PDHP-HEC-E-1252 | 2022-11-02 | 19 | X |  |  | APV
AR | HEC-PROJ-AR-0011 | 0 | HST | Fire and Process Water Pump Station(100-SHT-SC-300) | Arch. Part |  | 2021-07-16 | 2021-07-28 | 12 | [9 empty] | Signed IFC 미접수로 ASC 제출 대기중
AR | HEC-PROJ-AR-0012 | 0 | HST | Terminal Control Room Building(1000-CR-22) | Arch. Part |  | 2021-07-07 | 2021-07-16 | 9 | [9 empty] | Signed IFC 미접수로 ASC 제출 대기중
AR | HEC-PROJ-AR-0013 | 0 | HST | Terminal Control Room Building(1000-CR-22) | RC Part |  | 2021-07-07 | 2021-07-20 | 13 |  |  |  | 00-HEC-PDHP-E-2091 | 2021-08-05 | 05-PDHP-HEC-E-0479 | 2021-08-17 | 12 | X |  |  | AWC
AR |  | 0 | HST |  | RC Part | [7 empty] | 05-HEC-PDHP-E-0633 | 2021-09-21 | 05-PDHP-HEC-E-0523 | 2021-09-23 | 2 | X | RBP Decision 접수 후, Rev.올려서 ASC 재 제출예정 (발주처/FE 협의 완료) |  | REJ
AR | HEC-PROJ-AR-0014 | 0 | HST | Changed Room Height of Terminal Control Room Building (1000-CR-22) | - |  | 2021-07-27 | 2021-07-28 | 1 |  |  |  | 00-HEC-PDHP-E-2499 | 2021-10-20 | 05-PDHP-HEC-E-0558 | 2021-11-03 | 14 | X |  |  | AWC
|  |  | HST |  | - |  | 2021-11-08 | 2021-11-09 | 1 |  |  |  | 00-HEC-PDHP-E-2612 | 2021-11-16 | 05-PDHP-HEC-E-0584 | 2021-12-02 | 16 | X |  |  | AWC
|  |  | HST | [9 empty] | 05-HEC-PDHP-E-0752 | 2021-12-25 | 05-PDHP-HEC-E-0617 | 2022-01-15 | 21 |  |  |  | APV
AR | HEC-PROJ-AR-0015 |  | HST | Deluege Vavle Shelter(HST No.1,2,3,4) | New Object |  | 2021-08-11 | 2021-09-07 | 27 |  |  |  | 00-HEC-PDHP-E-2397 | 2021-09-30 | 05-PDHP-HEC-E-0545 | 2021-10-14 | 14 | X |  |  | REJ
AR |  |  | HST | [9 empty] | 05-HEC-PDHP-E-0675 | 2021-10-15 | 05-PDHP-HEC-E-0558 | 2021-11-03 | 19 | X | 코멘트 관련 FE/발주처 협의 요청 필요 Revised ASC는 2nd BP Decision 접수 후 제출 (발주처 코멘트) |  | AWC
|  |  | HST | [9 empty] | 05-HEC-PDHP-E-1177 | 2022-10-14 | 05-PDHP-HEC-E-1252 | 2022-11-02 | 19 | X |  |  | APV
AR | HEC-PROJ-AR-0016 | 0 | HST | Changed Facade Finish Schedule of Building and Shelter | - |  | 2021-12-22 | [5 empty] | 00-HEC-PDHP-E-2950 | 2022-02-02 | 05-PDHP-HEC-E-0655 | 2022-02-09 | 7 | X | 서명본 누락 |  | APV
AR | HEC-PROJ-AR-0017 | 0 | HST | Change in Fire Resistant Wall Concept of Pipe Shaft on Ground Floor of 1000-CR-22 | - |  | 2021-12-22 | [5 empty] | 00-HEC-PDHP-E-2951 | 2022-02-02 | 05-PDHP-HEC-E-0673 | 2022-02-18 | 16 | X |  |  | AWC
|  |  | HST | [9 empty] | 05-HEC-PDHP-E-0946 | 2022-05-27
|  |  | HST | [9 empty] | 05-HEC-PDHP-E-1175 | 2022-10-14 | 05-PDHP-HEC-E-1252 | 2022-11-02 | 19 | X |  |  | APV
AR | HEC-PROJ-AR-0018 | 0 | HST | Deluge valve shelter B | AR part |  | 2022-11-28
-

## 전기
Master Status of Authors Supervision Card (EL)
Discipline | ASC No. | Revision | Unit | Building/ Item name | Part of Object | Title (Brief description) | Prochem/ Projomos |  |  | Licensor Engineer Signature |  |  | Owner |  |  |  |  | Owner Signature | REMARK
[7 empty] | Submitted Date | Received Date | Duration | Submitted Date | Received Date | Duration | Email No.(HEC) | Submitted Date | Email No.(Owner) | Received Date | Duration
건축 Only

## 항만
Master Status of Authors Supervision Card (MA)
Discipline | ASC No. | Revision | Unit | Building/ Item name | Part of Object | Title (Brief description) | Prochem/ Projomos |  |  | Licensor Engineer Signature |  |  | Owner |  |  |  |  | Owner Signature | REMARK
[7 empty] | Submitted Date | Received Date | Duration | Submitted Date | Received Date | Duration | Email No.(HEC) | Submitted Date | Email No.(Owner) | Received Date | Duration
건축 Only