## 변경사항
No. | Item | Description | Date | Requestor | Rev. No.(Old) | Remark
1 | Cryogenic (Cold protection) | Cryogenic (Cold protection) 추가 | 2022-06-28 | 시공 | 1
2 | Site Instruction | Site Instruction 추가 | 2022-12-26 | 사업
3 | Repair Work for Fireproofing | Repair Work for Fireproofing 추가 | 2023-07-27 | BI시공
4 | Coating | Coating관련 Work Master 추가 | 2023-12-07 | 설계

## FP
|  | to Be | to Be | to Be | 조건 | 체계조건 | Work Pack | Work Pack | Group | Group | Group | Group | Group | Group | Sequence | Sequence | BOQ | BOQ | To Be | To Be | To Be | To Be 산출 Logic, Factor | To Be 산출 Logic, Factor | To Be 산출 Logic, Factor | To Be 산출 Logic, Factor | To Be 산출 Logic, Factor | To Be 산출 Logic, Factor | To Be 산출 Logic, Factor | To Be 산출 Logic, Factor | To Be 산출 Logic, Factor | To Be 산출 Logic, Factor | To Be 산출 Logic, Factor | To Be
|  | Work Group | Sequence | Work Master | 데이터 사양 | Level | L00 | L00 | L01 | L01 | L02 | L02 | L03 | L03 | L04 | L04 | B01 | B02 | UoM1 | UoM2 | BOQ 산출유형 | BOQ 산출 Logic | F 01 |  | F 02 |  | F 03 |  | F 04 |  | F 05 |  | 평가클래스 | Remarks | Group combination | 속성 combination | Full combination | 속성레벨 combination | Full combination (속성레벨) | 속성레벨 유형 | BOQ속성레벨 combination | ATT_Combi_Qty | ATT_TYPE_Key_Level | ATT_TYPE_Key_Value | ATT_TYPE_Key_Value_Description | BOQ_Combi | BOQ_Type | BOQ_Combi_Qty | BOQ_TYPE_Key_Level | BOQ_TYPE_Key_Value | BOQ_TYPE_Key_Value_Description
[6 empty] | 특성 | Code | aWBS | Code | Work Group | Code | Work Group | Code | Work Group | Code | Attribute | BOQ_Spec | BOQ_Spec | UoM 01 | UoM 02 | BOQ Type |  | Logic Factor 01 |  | Logic Factor 02 |  | Logic Factor 03 |  | Logic Factor 04 |  | Logic Factor 05 |  | CoA
|  | Varchar2 | Number | Varchar2 |  | 데이터 사양 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Number | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Varchar2 | Number
생성 |  | Auto | Auto | Auto |  | 입력유형 | key-in | key-in | key-in | I/F-WBS library | key-in | I/F-WBS library | key-in | I/F-WBS library | key in | key in | key in | key in | Group | Sequnce | key in | key in | key in | key in | key in | key in | key in | key in | key in | key in | key in | key in | key in
폐기 |  | 8 | 5 | 14 | (부서) | 데이터 길이 | 2 | 80 | 3 | 80 | 2 | 80 | 3 | 80 | 2 | 80 | 80 | 80 | 3 | 3 | 1 | 80 | 1 | 20 | 1 | 20 | 1 | 20 | 1 | 20 | 1 | 20 | 7
수정 | [5 empty] | UoM | [11 empty] | mm
Status | Date | Work Group | Sequence | Work Master | Discipline | 구분 | Code | Work Pack | Code | Category(Large) | Code | Category(Middle) | Code | Category(Small) | Code | Fire Proof Rating | Material | Thickness | UoM1 | UoM2 | BOQ_Type | Formula | Code | Factor01 | Code | Factor02 | Code | Factor03 | Code | Factor04 | Code | Factor05 | CoA |  | Group combination | Attribute combination | Value_Full_combination | Attribute_Level combination | Group_Attribute_Full_combination | Group_Combination_Type | Group_BOQ Attribute_combination | ATT_Combi_Qty | ATT_TYPE_Key_Level | ATT_TYPE_Key_Value | ATT_TYPE_Key_Value_Description | BOQ_Combi | BOQ_Type | BOQ_Combi_Qty | BOQ_TYPE_Key_Level | BOQ_TYPE_Key_Value | BOQ_TYPE_Key_Value_Description
Status | Date | WG_CD | SQ_CD | WM_CD | Disc | Disc_Item_No | WP_CD | WP_Desc | L01_CD | L01_Desc | L02_CD | L02_Desc | L03_CD | L03_Desc | L04_CD | L04_Desc | B01 | B02 | UoM1 | UoM2 | BOQ_Type | BOQ_Formula | F01_CD | F01_Desc | F02_CD | F02_Desc | F03_CD | F03_Desc | F04_CD | F04_Desc | F05_CD | F05_Desc | CoA | Remarks | WG_Combi | ATT_Combi | WG_ATT_Combi | ATT_LV_Combi | WG_ATT_LV_Combi | ATT_Combi_Type | BOQ_Combi | ATT_Combi_Qt | ATT_TYPE_Key_LV | ATT_TYPE_Key_VL | ATT_TYPE_Key_Desc | WG_BOQ_Combi | BOQ_Combi_Type | BOQ_Combi_Qt | BOQ_TYPE_Key_LV | BOQ_TYPE_Key_VL | BOQ_TYPE_Key_Desc
수정 | 2021-11-19 | F01AA000 | 00001 | F01AA000-00001 | FP | 1 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AA | Dense Concrete | 000 | - | 01 | 0.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AA000 | 01 | F01AA000-01 | L04 | F01AA000-L04 | A | B01B02 | 1 |  |  |  | F01AA000-B01B02 | A | 1
수정 | 2021-11-19 | F01AA000 | 00002 | F01AA000-00002 | FP | 2 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AA | Dense Concrete | 000 | - | 02 | 1 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AA000 | 02 | F01AA000-02 | L04 | F01AA000-L04 | A | B01B02 | 1 |  |  |  | F01AA000-B01B02 | A | 1
수정 | 2021-11-19 | F01AA000 | 00003 | F01AA000-00003 | FP | 3 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AA | Dense Concrete | 000 | - | 03 | 1.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AA000 | 03 | F01AA000-03 | L04 | F01AA000-L04 | A | B01B02 | 1 |  |  |  | F01AA000-B01B02 | A | 1
수정 | 2021-11-19 | F01AA000 | 00004 | F01AA000-00004 | FP | 4 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AA | Dense Concrete | 000 | - | 04 | 2 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AA000 | 04 | F01AA000-04 | L04 | F01AA000-L04 | A | B01B02 | 1 |  |  |  | F01AA000-B01B02 | A | 1
수정 | 2021-11-19 | F01AA000 | 00005 | F01AA000-00005 | FP | 5 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AA | Dense Concrete | 000 | - | 05 | 2.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AA000 | 05 | F01AA000-05 | L04 | F01AA000-L04 | A | B01B02 | 1 |  |  |  | F01AA000-B01B02 | A | 1
수정 | 2021-11-19 | F01AA000 | 00006 | F01AA000-00006 | FP | 6 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AA | Dense Concrete | 000 | - | 06 | 3 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AA000 | 06 | F01AA000-06 | L04 | F01AA000-L04 | A | B01B02 | 1 |  |  |  | F01AA000-B01B02 | A | 1
수정 | 2021-11-19 | F01AA000 | 00007 | F01AA000-00007 | FP | 7 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AA | Dense Concrete | 000 | - | 07 | 3.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AA000 | 07 | F01AA000-07 | L04 | F01AA000-L04 | A | B01B02 | 1 |  |  |  | F01AA000-B01B02 | A | 1
수정 | 2021-11-19 | F01AA000 | 00008 | F01AA000-00008 | FP | 8 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AA | Dense Concrete | 000 | - | 08 | 4 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AA000 | 08 | F01AA000-08 | L04 | F01AA000-L04 | A | B01B02 | 1 |  |  |  | F01AA000-B01B02 | A | 1
수정 | 2021-11-19 | F01AA000 | 00009 | F01AA000-00009 | FP | 9 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AA | Dense Concrete | 000 | - | 09 | Others (UL1709 rating) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AA000 | 09 | F01AA000-09 | L04 | F01AA000-L04 | A | B01B02 | 1 |  |  |  | F01AA000-B01B02 | A | 1
|  | F01AB000 | 00001 | F01AB000-00001 | FP | 10 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 01 | 0.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AB000 | 01 | F01AB000-01 | L04 | F01AB000-L04 | A | B01B02 | 1 |  |  |  | F01AB000-B01B02 | A | 1
|  | F01AB000 | 00002 | F01AB000-00002 | FP | 11 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 02 | 1 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AB000 | 02 | F01AB000-02 | L04 | F01AB000-L04 | A | B01B02 | 1 |  |  |  | F01AB000-B01B02 | A | 1
|  | F01AB000 | 00003 | F01AB000-00003 | FP | 12 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 03 | 1.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AB000 | 03 | F01AB000-03 | L04 | F01AB000-L04 | A | B01B02 | 1 |  |  |  | F01AB000-B01B02 | A | 1
|  | F01AB000 | 00004 | F01AB000-00004 | FP | 13 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 04 | 2 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AB000 | 04 | F01AB000-04 | L04 | F01AB000-L04 | A | B01B02 | 1 |  |  |  | F01AB000-B01B02 | A | 1
|  | F01AB000 | 00005 | F01AB000-00005 | FP | 14 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 05 | 2.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AB000 | 05 | F01AB000-05 | L04 | F01AB000-L04 | A | B01B02 | 1 |  |  |  | F01AB000-B01B02 | A | 1
|  | F01AB000 | 00006 | F01AB000-00006 | FP | 15 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 06 | 3 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AB000 | 06 | F01AB000-06 | L04 | F01AB000-L04 | A | B01B02 | 1 |  |  |  | F01AB000-B01B02 | A | 1
|  | F01AB000 | 00007 | F01AB000-00007 | FP | 16 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 07 | 3.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AB000 | 07 | F01AB000-07 | L04 | F01AB000-L04 | A | B01B02 | 1 |  |  |  | F01AB000-B01B02 | A | 1
|  | F01AB000 | 00008 | F01AB000-00008 | FP | 17 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 08 | 4 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AB000 | 08 | F01AB000-08 | L04 | F01AB000-L04 | A | B01B02 | 1 |  |  |  | F01AB000-B01B02 | A | 1
|  | F01AB000 | 00009 | F01AB000-00009 | FP | 18 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 09 | Others (UL1709 rating) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AB000 | 09 | F01AB000-09 | L04 | F01AB000-L04 | A | B01B02 | 1 |  |  |  | F01AB000-B01B02 | A | 1
|  | F01AC000 | 00001 | F01AC000-00001 | FP | 19 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 01 | 0.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 01 | F01AC000-01 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00002 | F01AC000-00002 | FP | 20 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 02 | 1 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 02 | F01AC000-02 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00003 | F01AC000-00003 | FP | 21 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 03 | 1.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 03 | F01AC000-03 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00004 | F01AC000-00004 | FP | 22 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 04 | 2 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 04 | F01AC000-04 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00005 | F01AC000-00005 | FP | 23 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 05 | 2.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 05 | F01AC000-05 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00006 | F01AC000-00006 | FP | 24 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 06 | 3 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 06 | F01AC000-06 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00007 | F01AC000-00007 | FP | 25 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 07 | 3.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 07 | F01AC000-07 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00008 | F01AC000-00008 | FP | 26 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 08 | 4 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 08 | F01AC000-08 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00009 | F01AC000-00009 | FP | 27 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 10 | 0.5 hr. rating (UL 263) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 10 | F01AC000-10 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00010 | F01AC000-00010 | FP | 28 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 11 | 1 hr. rating (UL 263) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 11 | F01AC000-11 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00011 | F01AC000-00011 | FP | 29 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 12 | 1.5 hr. rating (UL 263) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 12 | F01AC000-12 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00012 | F01AC000-00012 | FP | 30 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 13 | 2 hr. rating (UL 263) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 13 | F01AC000-13 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00013 | F01AC000-00013 | FP | 31 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 14 | 2.5 hr. rating (UL 263) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 14 | F01AC000-14 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00014 | F01AC000-00014 | FP | 32 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 15 | 3 hr. rating (UL 263) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 15 | F01AC000-15 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00015 | F01AC000-00015 | FP | 33 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 16 | 3.5 hr. rating (UL 263) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 16 | F01AC000-16 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00016 | F01AC000-00016 | FP | 34 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 17 | 4 hr. rating (UL 263) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 17 | F01AC000-17 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00017 | F01AC000-00017 | FP | 35 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 18 | Others (UL263 rating) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 18 | F01AC000-18 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AC000 | 00018 | F01AC000-00018 | FP | 36 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 09 | Others (UL1709 rating) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AC000 | 09 | F01AC000-09 | L04 | F01AC000-L04 | A | B01B02 | 1 |  |  |  | F01AC000-B01B02 | A | 1
|  | F01AD000 | 00001 | F01AD000-00001 | FP | 37 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AD | Top Coat for Cementitious Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AD000 |  | F01AD000- |  | F01AD000- | Z | B01B02 | 1 |  |  |  | F01AD000-B01B02 | A | 1
생성 | 2023-12-07 | F01AF000 | 00001 | F01AF000-00001 | FP | 100 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AF | Cryogenic (Cold protection) | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AF000 |  | F01AF000- |  | F01AF000- | Z | B01B02 | 1 |  |  |  | F01AF000-B01B02 | A | 1
생성 | 2023-12-07 | F01AM000 | 00001 | F01AM000-00001 | FP | 101 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AM | Top Coat for Dense Concrete Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AM000 |  | F01AM000- |  | F01AM000- | Z | B01B02 | 1 |  |  |  | F01AM000-B01B02 | A | 1
생성 | 2023-12-07 | F01AP000 | 00001 | F01AP000-00001 | FP | 102 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AP | Top Coat for Cryogenic (Cold protection) Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AP000 |  | F01AP000- |  | F01AP000- | Z | B01B02 | 1 |  |  |  | F01AP000-B01B02 | A | 1
생성 | 2023-12-07 | F01AQ000 | 00001 | F01AQ000-00001 | FP | 103 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AQ | Top Coat for Intumescent Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AQ000 |  | F01AQ000- |  | F01AQ000- | Z | B01B02 | 1 |  |  |  | F01AQ000-B01B02 | A | 1
생성 | 2023-12-07 | F01AR000 | 00001 | F01AR000-00001 | FP | 104 | 34 | Fire Proofing Work | F01 | Building/Shelter Fire Proofing Work | AR | Intermediate and top Coat for Intumescent Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F01 | Building/Shelter Fire Proofing Work | 4301018 |  | F01AR000 |  | F01AR000- |  | F01AR000- | Z | B01B02 | 1 |  |  |  | F01AR000-B01B02 | A | 1
수정 | 2021-11-19 | F02AA000 | 00001 | F02AA000-00001 | FP | 38 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AA | Dense Concrete | 000 | - | 01 | 0.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AA000 | 01 | F02AA000-01 | L04 | F02AA000-L04 | A | B01B02 | 1 |  |  |  | F02AA000-B01B02 | A | 1
수정 | 2021-11-19 | F02AA000 | 00002 | F02AA000-00002 | FP | 39 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AA | Dense Concrete | 000 | - | 02 | 1 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AA000 | 02 | F02AA000-02 | L04 | F02AA000-L04 | A | B01B02 | 1 |  |  |  | F02AA000-B01B02 | A | 1
수정 | 2021-11-19 | F02AA000 | 00003 | F02AA000-00003 | FP | 40 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AA | Dense Concrete | 000 | - | 03 | 1.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AA000 | 03 | F02AA000-03 | L04 | F02AA000-L04 | A | B01B02 | 1 |  |  |  | F02AA000-B01B02 | A | 1
수정 | 2021-11-19 | F02AA000 | 00004 | F02AA000-00004 | FP | 41 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AA | Dense Concrete | 000 | - | 04 | 2 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AA000 | 04 | F02AA000-04 | L04 | F02AA000-L04 | A | B01B02 | 1 |  |  |  | F02AA000-B01B02 | A | 1
수정 | 2021-11-19 | F02AA000 | 00005 | F02AA000-00005 | FP | 42 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AA | Dense Concrete | 000 | - | 05 | 2.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AA000 | 05 | F02AA000-05 | L04 | F02AA000-L04 | A | B01B02 | 1 |  |  |  | F02AA000-B01B02 | A | 1
수정 | 2021-11-19 | F02AA000 | 00006 | F02AA000-00006 | FP | 43 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AA | Dense Concrete | 000 | - | 06 | 3 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AA000 | 06 | F02AA000-06 | L04 | F02AA000-L04 | A | B01B02 | 1 |  |  |  | F02AA000-B01B02 | A | 1
수정 | 2021-11-19 | F02AA000 | 00007 | F02AA000-00007 | FP | 44 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AA | Dense Concrete | 000 | - | 07 | 3.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AA000 | 07 | F02AA000-07 | L04 | F02AA000-L04 | A | B01B02 | 1 |  |  |  | F02AA000-B01B02 | A | 1
수정 | 2021-11-19 | F02AA000 | 00008 | F02AA000-00008 | FP | 45 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AA | Dense Concrete | 000 | - | 08 | 4 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AA000 | 08 | F02AA000-08 | L04 | F02AA000-L04 | A | B01B02 | 1 |  |  |  | F02AA000-B01B02 | A | 1
수정 | 2021-11-19 | F02AA000 | 00009 | F02AA000-00009 | FP | 46 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AA | Dense Concrete | 000 | - | 09 | Others (UL1709 rating) | Material: ( ) | THK=( )mm | M3 | M3 | 4 |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AA000 | 09 | F02AA000-09 | L04 | F02AA000-L04 | A | B01B02 | 1 |  |  |  | F02AA000-B01B02 | A | 1
|  | F02AB000 | 00001 | F02AB000-00001 | FP | 47 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 01 | 0.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AB000 | 01 | F02AB000-01 | L04 | F02AB000-L04 | A | B01B02 | 1 |  |  |  | F02AB000-B01B02 | A | 1
|  | F02AB000 | 00002 | F02AB000-00002 | FP | 48 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 02 | 1 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AB000 | 02 | F02AB000-02 | L04 | F02AB000-L04 | A | B01B02 | 1 |  |  |  | F02AB000-B01B02 | A | 1
|  | F02AB000 | 00003 | F02AB000-00003 | FP | 49 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 03 | 1.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AB000 | 03 | F02AB000-03 | L04 | F02AB000-L04 | A | B01B02 | 1 |  |  |  | F02AB000-B01B02 | A | 1
|  | F02AB000 | 00004 | F02AB000-00004 | FP | 50 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 04 | 2 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AB000 | 04 | F02AB000-04 | L04 | F02AB000-L04 | A | B01B02 | 1 |  |  |  | F02AB000-B01B02 | A | 1
|  | F02AB000 | 00005 | F02AB000-00005 | FP | 51 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 05 | 2.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AB000 | 05 | F02AB000-05 | L04 | F02AB000-L04 | A | B01B02 | 1 |  |  |  | F02AB000-B01B02 | A | 1
|  | F02AB000 | 00006 | F02AB000-00006 | FP | 52 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 06 | 3 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AB000 | 06 | F02AB000-06 | L04 | F02AB000-L04 | A | B01B02 | 1 |  |  |  | F02AB000-B01B02 | A | 1
|  | F02AB000 | 00007 | F02AB000-00007 | FP | 53 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 07 | 3.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AB000 | 07 | F02AB000-07 | L04 | F02AB000-L04 | A | B01B02 | 1 |  |  |  | F02AB000-B01B02 | A | 1
|  | F02AB000 | 00008 | F02AB000-00008 | FP | 54 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 08 | 4 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AB000 | 08 | F02AB000-08 | L04 | F02AB000-L04 | A | B01B02 | 1 |  |  |  | F02AB000-B01B02 | A | 1
|  | F02AB000 | 00009 | F02AB000-00009 | FP | 55 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 09 | Others (UL1709 rating) | Material: ( ) | THK=( )mm | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AB000 | 09 | F02AB000-09 | L04 | F02AB000-L04 | A | B01B02 | 1 |  |  |  | F02AB000-B01B02 | A | 1
|  | F02AC000 | 00001 | F02AC000-00001 | FP | 56 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 01 | 0.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AC000 | 01 | F02AC000-01 | L04 | F02AC000-L04 | A | B01B02 | 1 |  |  |  | F02AC000-B01B02 | A | 1
|  | F02AC000 | 00002 | F02AC000-00002 | FP | 57 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 02 | 1 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AC000 | 02 | F02AC000-02 | L04 | F02AC000-L04 | A | B01B02 | 1 |  |  |  | F02AC000-B01B02 | A | 1
|  | F02AC000 | 00003 | F02AC000-00003 | FP | 58 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 03 | 1.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AC000 | 03 | F02AC000-03 | L04 | F02AC000-L04 | A | B01B02 | 1 |  |  |  | F02AC000-B01B02 | A | 1
|  | F02AC000 | 00004 | F02AC000-00004 | FP | 59 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 04 | 2 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AC000 | 04 | F02AC000-04 | L04 | F02AC000-L04 | A | B01B02 | 1 |  |  |  | F02AC000-B01B02 | A | 1
|  | F02AC000 | 00005 | F02AC000-00005 | FP | 60 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 05 | 2.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AC000 | 05 | F02AC000-05 | L04 | F02AC000-L04 | A | B01B02 | 1 |  |  |  | F02AC000-B01B02 | A | 1
|  | F02AC000 | 00006 | F02AC000-00006 | FP | 61 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 06 | 3 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AC000 | 06 | F02AC000-06 | L04 | F02AC000-L04 | A | B01B02 | 1 |  |  |  | F02AC000-B01B02 | A | 1
|  | F02AC000 | 00007 | F02AC000-00007 | FP | 62 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 07 | 3.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AC000 | 07 | F02AC000-07 | L04 | F02AC000-L04 | A | B01B02 | 1 |  |  |  | F02AC000-B01B02 | A | 1
|  | F02AC000 | 00008 | F02AC000-00008 | FP | 63 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 08 | 4 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AC000 | 08 | F02AC000-08 | L04 | F02AC000-L04 | A | B01B02 | 1 |  |  |  | F02AC000-B01B02 | A | 1
|  | F02AC000 | 00009 | F02AC000-00009 | FP | 64 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AC | Intumescent Coating Type | 000 | - | 09 | Others (UL1709 rating) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AC000 | 09 | F02AC000-09 | L04 | F02AC000-L04 | A | B01B02 | 1 |  |  |  | F02AC000-B01B02 | A | 1
|  | F02AD000 | 00001 | F02AD000-00001 | FP | 65 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AD | Top Coat for Cementitious Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AD000 |  | F02AD000- |  | F02AD000- | Z | B01B02 | 1 |  |  |  | F02AD000-B01B02 | A | 1
생성 | 2022-06-28 | F02AF000 | 00001 | F02AF000-00001 | FP | 94 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AF | Cryogenic (Cold protection) | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AF000 |  | F02AF000- |  | F02AF000- | Z | B01B02 | 1 |  |  |  | F02AF000-B01B02 | A | 1
생성 | 2023-12-07 | F02AM000 | 00001 | F02AM000-00001 | FP | 105 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AM | Top Coat for Dense Concrete Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AM000 |  | F02AM000- |  | F02AM000- | Z | B01B02 | 1 |  |  |  | F02AM000-B01B02 | A | 1
생성 | 2023-12-07 | F02AP000 | 00001 | F02AP000-00001 | FP | 106 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AP | Top Coat for Cryogenic (Cold protection) Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AP000 |  | F02AP000- |  | F02AP000- | Z | B01B02 | 1 |  |  |  | F02AP000-B01B02 | A | 1
생성 | 2023-12-07 | F02AQ000 | 00001 | F02AQ000-00001 | FP | 107 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AQ | Top Coat for Intumescent Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AQ000 |  | F02AQ000- |  | F02AQ000- | Z | B01B02 | 1 |  |  |  | F02AQ000-B01B02 | A | 1
생성 | 2023-12-07 | F02AR000 | 00001 | F02AR000-00001 | FP | 108 | 34 | Fire Proofing Work | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AR | Intermediate and top Coat for Intumescent Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 4 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | 4301018 |  | F02AR000 |  | F02AR000- |  | F02AR000- | Z | B01B02 | 1 |  |  |  | F02AR000-B01B02 | A | 1
수정 | 2021-11-19 | F03AA000 | 00001 | F03AA000-00001 | FP | 66 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AA | Dense Concrete | 000 | - | 01 | 0.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 3E |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AA000 | 01 | F03AA000-01 | L04 | F03AA000-L04 | A | B01B02 | 1 |  |  |  | F03AA000-B01B02 | A | 1
수정 | 2021-11-19 | F03AA000 | 00002 | F03AA000-00002 | FP | 67 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AA | Dense Concrete | 000 | - | 02 | 1 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 3E |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AA000 | 02 | F03AA000-02 | L04 | F03AA000-L04 | A | B01B02 | 1 |  |  |  | F03AA000-B01B02 | A | 1
수정 | 2021-11-19 | F03AA000 | 00003 | F03AA000-00003 | FP | 68 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AA | Dense Concrete | 000 | - | 03 | 1.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 3E |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AA000 | 03 | F03AA000-03 | L04 | F03AA000-L04 | A | B01B02 | 1 |  |  |  | F03AA000-B01B02 | A | 1
수정 | 2021-11-19 | F03AA000 | 00004 | F03AA000-00004 | FP | 69 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AA | Dense Concrete | 000 | - | 04 | 2 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 3E |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AA000 | 04 | F03AA000-04 | L04 | F03AA000-L04 | A | B01B02 | 1 |  |  |  | F03AA000-B01B02 | A | 1
수정 | 2021-11-19 | F03AA000 | 00005 | F03AA000-00005 | FP | 70 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AA | Dense Concrete | 000 | - | 05 | 2.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 3E |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AA000 | 05 | F03AA000-05 | L04 | F03AA000-L04 | A | B01B02 | 1 |  |  |  | F03AA000-B01B02 | A | 1
수정 | 2021-11-19 | F03AA000 | 00006 | F03AA000-00006 | FP | 71 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AA | Dense Concrete | 000 | - | 06 | 3 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 3E |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AA000 | 06 | F03AA000-06 | L04 | F03AA000-L04 | A | B01B02 | 1 |  |  |  | F03AA000-B01B02 | A | 1
수정 | 2021-11-19 | F03AA000 | 00007 | F03AA000-00007 | FP | 72 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AA | Dense Concrete | 000 | - | 07 | 3.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 3E |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AA000 | 07 | F03AA000-07 | L04 | F03AA000-L04 | A | B01B02 | 1 |  |  |  | F03AA000-B01B02 | A | 1
수정 | 2021-11-19 | F03AA000 | 00008 | F03AA000-00008 | FP | 73 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AA | Dense Concrete | 000 | - | 08 | 4 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M3 | M3 | 3E |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AA000 | 08 | F03AA000-08 | L04 | F03AA000-L04 | A | B01B02 | 1 |  |  |  | F03AA000-B01B02 | A | 1
수정 | 2021-11-19 | F03AA000 | 00009 | F03AA000-00009 | FP | 74 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AA | Dense Concrete | 000 | - | 09 | Others (UL1709 rating) | Material: ( ) | THK=( )mm | M3 | M3 | 3E |  | M2 | 대표물량 UoM | A | 20 | M2 | CBE LV2 UoM | A | 20 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AA000 | 09 | F03AA000-09 | L04 | F03AA000-L04 | A | B01B02 | 1 |  |  |  | F03AA000-B01B02 | A | 1
|  | F03AB000 | 00001 | F03AB000-00001 | FP | 75 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 01 | 0.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AB000 | 01 | F03AB000-01 | L04 | F03AB000-L04 | A | B01B02 | 1 |  |  |  | F03AB000-B01B02 | A | 1
|  | F03AB000 | 00002 | F03AB000-00002 | FP | 76 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 02 | 1 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AB000 | 02 | F03AB000-02 | L04 | F03AB000-L04 | A | B01B02 | 1 |  |  |  | F03AB000-B01B02 | A | 1
|  | F03AB000 | 00003 | F03AB000-00003 | FP | 77 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 03 | 1.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AB000 | 03 | F03AB000-03 | L04 | F03AB000-L04 | A | B01B02 | 1 |  |  |  | F03AB000-B01B02 | A | 1
|  | F03AB000 | 00004 | F03AB000-00004 | FP | 78 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 04 | 2 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AB000 | 04 | F03AB000-04 | L04 | F03AB000-L04 | A | B01B02 | 1 |  |  |  | F03AB000-B01B02 | A | 1
|  | F03AB000 | 00005 | F03AB000-00005 | FP | 79 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 05 | 2.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AB000 | 05 | F03AB000-05 | L04 | F03AB000-L04 | A | B01B02 | 1 |  |  |  | F03AB000-B01B02 | A | 1
|  | F03AB000 | 00006 | F03AB000-00006 | FP | 80 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 06 | 3 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AB000 | 06 | F03AB000-06 | L04 | F03AB000-L04 | A | B01B02 | 1 |  |  |  | F03AB000-B01B02 | A | 1
|  | F03AB000 | 00007 | F03AB000-00007 | FP | 81 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 07 | 3.5 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AB000 | 07 | F03AB000-07 | L04 | F03AB000-L04 | A | B01B02 | 1 |  |  |  | F03AB000-B01B02 | A | 1
|  | F03AB000 | 00008 | F03AB000-00008 | FP | 82 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 08 | 4 hr. rating (UL 1709) | Material: ( ) | THK=( )mm | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AB000 | 08 | F03AB000-08 | L04 | F03AB000-L04 | A | B01B02 | 1 |  |  |  | F03AB000-B01B02 | A | 1
|  | F03AB000 | 00009 | F03AB000-00009 | FP | 83 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AB | Lightweight Cementitious | 000 | - | 09 | Others (UL1709 rating) | Material: ( ) | THK=( )mm | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AB000 | 09 | F03AB000-09 | L04 | F03AB000-L04 | A | B01B02 | 1 |  |  |  | F03AB000-B01B02 | A | 1
|  | F03AD000 | 00001 | F03AD000-00001 | FP | 93 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AD | Top Coat for Cementitious Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AD000 |  | F03AD000- |  | F03AD000- | Z | B01B02 | 1 |  |  |  | F03AD000-B01B02 | A | 1
|  | F03AE000 | 00001 | F03AE000-00001 | FP | 84 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AE | Epoxy Based Intumescent Coating Type | 000 | - | 01 | 0.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AE000 | 01 | F03AE000-01 | L04 | F03AE000-L04 | A | B01B02 | 1 |  |  |  | F03AE000-B01B02 | A | 1
|  | F03AE000 | 00002 | F03AE000-00002 | FP | 85 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AE | Epoxy Based Intumescent Coating Type | 000 | - | 02 | 1 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AE000 | 02 | F03AE000-02 | L04 | F03AE000-L04 | A | B01B02 | 1 |  |  |  | F03AE000-B01B02 | A | 1
|  | F03AE000 | 00003 | F03AE000-00003 | FP | 86 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AE | Epoxy Based Intumescent Coating Type | 000 | - | 03 | 1.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AE000 | 03 | F03AE000-03 | L04 | F03AE000-L04 | A | B01B02 | 1 |  |  |  | F03AE000-B01B02 | A | 1
|  | F03AE000 | 00004 | F03AE000-00004 | FP | 87 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AE | Epoxy Based Intumescent Coating Type | 000 | - | 04 | 2 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AE000 | 04 | F03AE000-04 | L04 | F03AE000-L04 | A | B01B02 | 1 |  |  |  | F03AE000-B01B02 | A | 1
|  | F03AE000 | 00005 | F03AE000-00005 | FP | 88 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AE | Epoxy Based Intumescent Coating Type | 000 | - | 05 | 2.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AE000 | 05 | F03AE000-05 | L04 | F03AE000-L04 | A | B01B02 | 1 |  |  |  | F03AE000-B01B02 | A | 1
|  | F03AE000 | 00006 | F03AE000-00006 | FP | 89 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AE | Epoxy Based Intumescent Coating Type | 000 | - | 06 | 3 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AE000 | 06 | F03AE000-06 | L04 | F03AE000-L04 | A | B01B02 | 1 |  |  |  | F03AE000-B01B02 | A | 1
|  | F03AE000 | 00007 | F03AE000-00007 | FP | 90 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AE | Epoxy Based Intumescent Coating Type | 000 | - | 07 | 3.5 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AE000 | 07 | F03AE000-07 | L04 | F03AE000-L04 | A | B01B02 | 1 |  |  |  | F03AE000-B01B02 | A | 1
|  | F03AE000 | 00008 | F03AE000-00008 | FP | 91 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AE | Epoxy Based Intumescent Coating Type | 000 | - | 08 | 4 hr. rating (UL 1709) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AE000 | 08 | F03AE000-08 | L04 | F03AE000-L04 | A | B01B02 | 1 |  |  |  | F03AE000-B01B02 | A | 1
|  | F03AE000 | 00009 | F03AE000-00009 | FP | 92 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AE | Epoxy Based Intumescent Coating Type | 000 | - | 09 | Others (UL1709 rating) | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 1 | 1 | M2 | CBE LV2 UoM | 1 | 1 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AE000 | 09 | F03AE000-09 | L04 | F03AE000-L04 | A | B01B02 | 1 |  |  |  | F03AE000-B01B02 | A | 1
생성 | 2022-06-28 | F03AF000 | 00001 | F03AF000-00001 | FP | 95 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AF | Cryogenic (Cold protection) | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AF000 |  | F03AF000- |  | F03AF000- | Z | B01B02 | 1 |  |  |  | F03AF000-B01B02 | A | 1
생성 | 2023-12-07 | F03AM000 | 00001 | F03AM000-00001 | FP | 109 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AM | Top Coat for Dense Concrete Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AM000 |  | F03AM000- |  | F03AM000- | Z | B01B02 | 1 |  |  |  | F03AM000-B01B02 | A | 1
생성 | 2023-12-07 | F03AP000 | 00001 | F03AP000-00001 | FP | 110 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AP | Top Coat for Cryogenic (Cold protection) Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AP000 |  | F03AP000- |  | F03AP000- | Z | B01B02 | 1 |  |  |  | F03AP000-B01B02 | A | 1
생성 | 2023-12-07 | F03AQ000 | 00001 | F03AQ000-00001 | FP | 111 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AQ | Top Coat for Intumescent Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AQ000 |  | F03AQ000- |  | F03AQ000- | Z | B01B02 | 1 |  |  |  | F03AQ000-B01B02 | A | 1
생성 | 2023-12-07 | F03AR000 | 00001 | F03AR000-00001 | FP | 112 | 34 | Fire Proofing Work | F03 | Equipment Fire Proofing Work | AR | Intermediate and top Coat for Intumescent Fire Proofing | 000 | - |  |  | Material: ( ) | DFT=( )㎛ | M2 | M2 | 3E |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F03 | Equipment Fire Proofing Work | 4301018 |  | F03AR000 |  | F03AR000- |  | F03AR000- | Z | B01B02 | 1 |  |  |  | F03AR000-B01B02 | A | 1
생성 | 2023-07-27 | F04ZZ000 | 00001 | F04ZZ000-00001 | FP | 99 | 34 | Fire Proofing Work | F04 | Repair Work for Fireproofing | ZZ | - | 000 | - |  |  |  |  | Point | Point | 5 |  | M2 | 대표물량 UoM | 0 | 0 | M2 | CBE LV2 UoM | 0 | 0 | F04 | Repair Work for Fireproofing | 4301018 |  | F04ZZ000 |  | F04ZZ000- |  | F04ZZ000- | Z |  | 1 |  |  |  | F04ZZ000- | Z | 1
생성 | 2022-12-26 | F10SA000 | 00001 | F10SA000-00001 | FP | 96 | 00 | General / Common Work | F10 | Site Instruction | SA | General / Common Work (Other Work) | 000 | - |  |  |  |  | LOT | LOT | 5 | [11 empty] | 4301018 |  | F10SA000 |  | F10SA000- |  | F10SA000- | Z |  | 1 |  |  |  | F10SA000- | Z | 1
생성 | 2022-12-26 | F10SB000 | 00001 | F10SB000-00001 | FP | 97 | 00 | General / Common Work | F10 | Site Instruction | SB | Incentive of Subcontractor (Progress Expediting) | 000 | - |  |  |  |  | LOT | LOT | 5 | [11 empty] | 4301018 |  | F10SB000 |  | F10SB000- |  | F10SB000- | Z |  | 1 |  |  |  | F10SB000- | Z | 1
생성 | 2022-12-26 | F10SC000 | 00001 | F10SC000-00001 | FP | 98 | 00 | General / Common Work | F10 | Site Instruction | SC | Claim of Subcontractor | 000 | - |  |  |  |  | LOT | LOT | 5 | [11 empty] | 4301018 |  | F10SC000 |  | F10SC000- |  | F10SC000- | Z |  | 1 |  |  |  | F10SC000- | Z | 1

## 코드표
Code | 대분류 | Code | 중분류 | Code | 소분류 | Code | Rating
F01 | Building/Shelter Fire Proofing Work | AA | Dense Concrete |  |  | 01 | 0.5 hr. rating (UL 1709)
F02 | Pipe Rack/Equipment Steel Structure Fire Proofing Work | AB | Lightweight Cementitious |  |  | 02 | 1 hr. rating (UL 1709)
F03 | Equipment Fire Proofing Work | AC | Intumescent Coating Type |  |  | 03 | 1.5 hr. rating (UL 1709)
F10 | Site Instruction | AD | Top Coat for Cementitious Fire Proofing |  |  | 04 | 2 hr. rating (UL 1709)
F04 | Repair Work for Fireproofing | AE | Epoxy Based Intumescent Coating Type |  |  | 05 | 2.5 hr. rating (UL 1709)
|  | AF | Cryogenic (Cold protection) |  |  | 06 | 3 hr. rating (UL 1709)
|  | AM | Top Coat for Dense Concrete Fire Proofing |  |  | 07 | 3.5 hr. rating (UL 1709)
|  | AP | Top Coat for Cryogenic (Cold protection) Fire Proofing |  |  | 08 | 4 hr. rating (UL 1709)
|  | AQ | Top Coat for Intumescent Fire Proofing |  |  | 09 | Others (UL1709 rating)
|  | AR | Intermediate and Top Coat for Intumescent Fire Proofing |  |  | 10 | 0.5 hr. rating (UL 263)
|  | SA | General / Common Work (Other Work) |  |  | 11 | 1 hr. rating (UL 263)
|  | SB | Incentive of Subcontractor (Progress Expediting) |  |  | 12 | 1.5 hr. rating (UL 263)
|  | SC | Claim of Subcontractor |  |  | 13 | 2 hr. rating (UL 263)
[6 empty] | 14 | 2.5 hr. rating (UL 263)
[6 empty] | 15 | 3 hr. rating (UL 263)
[6 empty] | 16 | 3.5 hr. rating (UL 263)
[6 empty] | 17 | 4 hr. rating (UL 263)
[6 empty] | 18 | Others (UL263 rating)