## Data
Engineering DRAWING & DOCUMENT LIST
( PROJECT: OOOO 설계기술용역 )
(1169 EA) | [86 empty] | As of 2011-06-14
| DRAWING & | DISP. | Cate | ACT | REV | SH'T | SIZE | FWBS | Mile | UNIT | CODE | CODE | CODE |  | Preparation of Data |  |  |  | Completion of Draft |  |  |  | Issue for Approval |  |  |  | Completion of Approval |  |  |  | Issue for Construction |  |  |  | Completion of Construction | [52 empty] | LAST | LAST
S/N | DOCUMENT NUMBER |  | gory | ID | NO. | NO. |  |  | stone |  | 1 | 2 | 3 | DESCRIPTION | (10%) |  |  |  | (30%) |  |  |  | (70%) |  |  |  | (90%) |  |  |  | (95%) |  |  |  | (100%) | [51 empty] | Remarks | TR IN | TR OUT | Client No.
|  |  | (Class) | [11 empty] | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No. | SCH.(P) | SCH.(F) | ACT. | TR No.
1 | 1-83100-UA-112-102 | AR | A | 12E20 | 6 |  | A1 |  | 2 | 1 |  |  |  | S/T건물/GROUND FLOOR PLAN | 2008-12-01 |  | 2007-10-01 |  | 2008-12-15 |  | 2008-02-15 |  | 2008-12-31 |  | 2009-04-16 | 현엔영월 제09-427호 | 2009-01-15 |  | 2009-06-12 | 62302-54050006-773 | 2009-01-31 |  | 2009-08-25 | 현엔영월 제09-822호 | 2010-11-30 |  | 2010-07-22 | [50 empty] | 62302-54050006-773@2009-06-12@Rev-A@Sts-1 | 현엔영월 제10-291호@2010-07-12@Rev-6@Pur-C | 1-83100-UA-112-102
2 | 1-83100-UA-112-111 | AR | A | 12E20 | 1 |  | A1 |  | 2 | 1 |  |  |  | S/T건물/MAIN SECTION | 2008-12-01 |  | 2007-10-01 |  | 2008-12-15 |  | 2008-02-15 |  | 2008-12-31 |  | 2009-04-16 | 현엔영월 제09-427호 | 2009-01-15 |  | 2009-06-12 | 62302-54050006-773 | 2009-01-31 |  | 2009-08-25 | 현엔영월 제09-822호 | 2010-11-30 |  | 2010-07-22 | [50 empty] | 62302-54050006-773@2009-06-12@Rev-A@Sts-1 | 현엔영월 제09-1148호@2009-12-04@Rev-1@Pur-C | 1-83100-UA-112-111
3 | 1-83100-UA-113-201 | AR | A | 12A30 | 2 |  | A1 |  | 2 | 1 |  |  |  | S/T건물/FOUNDATION LOCATION PLAN | 2008-07-01 |  | 2008-02-29 |  | 2008-07-15 |  | 2008-04-14 |  | 2008-07-31 |  | 2008-07-03 | 현엔영월 제08-220호 | 2008-08-15 |  | 2008-09-02 | 62302-54050011-1114호 | 2008-08-31 |  | 2008-09-29 | 현엔영월 제08-428호 | 2010-11-30 |  | 2010-07-22 | [51 empty] | 현엔영월 제09-156호@2009-02-16@Rev-2@Pur-C | 1-83100-UA-113-201
4 | 1-83100-UA-113-306 | AR | A | 12B30 | 6 |  | A1 |  | 2 | 1 |  |  |  | S/T건물/ROOF FRAMING PLAN | 2008-07-01 |  | 2008-02-29 |  | 2008-07-15 |  | 2008-04-14 |  | 2008-07-31 |  | 2008-09-19 | 현엔영월 제08-393호 | 2008-09-30 |  | 2008-10-06 | 62302-54050011-1274호 | 2008-10-06 |  | 2008-10-17 | 현엔영월 제08-497호 | 2010-11-30 | [53 empty] | 현엔영월 제09-1148호@2009-12-04@Rev-6@Pur-C | 1-83100-UA-113-306
5 | 1-83100-UA-113-307 | AR | A | 12B30 | 6 |  | A1 |  | 2 | 1 |  |  |  | S/T건물/FRAMING ELEVATION | 2008-07-01 |  | 2008-02-29 |  | 2008-07-15 |  | 2008-04-14 |  | 2008-07-31 |  | 2008-09-19 | 현엔영월 제08-393호 | 2008-09-30 |  | 2008-10-06 | 62302-54050011-1274호 | 2008-10-06 |  | 2008-10-17 | 현엔영월 제08-497호 | 2010-11-30 | [53 empty] | 현엔영월 제09-1148호@2009-12-04@Rev-6@Pur-C | 1-83100-UA-113-307
6 | 1-83100-UA-113-312 | AR | A | 12B30 | 3 |  | A1 |  | 2 | 1 |  |  |  | S/T건물/GIRTH ELEVATION | 2008-07-01 |  | 2008-02-29 |  | 2008-07-15 |  | 2008-04-14 |  | 2008-07-31 |  | 2009-01-15 | 현엔영월 제09-046호 | 2008-08-15 |  | 2009-03-23 | 62302-54050006-367 | 2008-08-31 |  | 2009-04-30 | 현엔영월 제09-501호 | 2010-11-30 | [52 empty] | 62302-54050006-367@2009-03-23@Rev-B@Sts- | 현엔영월 제09-1148호@2009-12-04@Rev-3@Pur-C | 1-83100-UA-113-312
7 | 1-83100-UA-113-360 | AR | A | 12B30 | 0 |  | A1 |  | 2 | 1 |  |  |  | S/T건물/MISC. STEEL DETAIL | 2008-07-01 |  | 2008-02-29 |  | 2008-07-15 |  | 2008-04-14 |  | 2008-07-31 |  | 2008-09-19 | 현엔영월 제08-393호 | 2008-08-15 |  | 2008-10-06 | 62302-54050011-1274호 | 2008-08-31 |  | 2008-10-17 | 현엔영월 제08-497호 | 2010-11-30 | [53 empty] | 현엔영월 제08-497호@2008-10-17@Rev-0@Pur-C | 1-83100-UA-113-360
1 | 1-85500-UA-112-003 | AR | A | 14A30 | 3 |  | A1 |  | 2 | 1 |  |  |  | 주제어건물/INTERIOR FINISH SCHEDULE | 2009-01-01 |  | 2008-04-15 |  | 2009-01-15 |  | 2008-04-29 |  | 2009-01-31 |  | 2009-02-12 | 현엔영월 제09-136호 | 2009-02-15 |  | 2009-04-20 | 62302-54050006-497 | 2009-02-28 |  | 2009-07-14 | 현엔영월 제09-675호 | 2009-08-31 |  | 2009-08-31 | [50 empty] | 62302-54050006-497@2009-04-20@Rev-A@Sts- | 현엔영월 제10-233호@2010-06-01@Rev-3@Pur-C | 1-85500-UA-112-003
2 | 1-85500-UA-112-104 | AR | A | 14A30 | 1 |  | A1 |  | 2 | 1 |  |  |  | 주제어건물/3RD FLOOR PLAN | 2009-01-01 |  | 2008-04-15 |  | 2009-01-15 |  | 2008-04-29 |  | 2009-01-31 |  | 2009-02-12 | 현엔영월 제09-136호 | 2009-02-15 |  | 2009-04-20 | 62302-54050006-497 | 2009-02-28 |  | 2009-07-14 | 현엔영월 제09-675호 | 2009-08-31 |  | 2009-08-31 | [50 empty] | 62302-54050006-497@2009-04-20@Rev-A@Sts- | 현엔영월 제09-1143호@2009-11-30@Rev-1@Pur-C | 1-85500-UA-112-104
3 | 1-85500-UA-112-108 | AR | A | 14A30 | 2 |  | A1 |  | 2 | 1 |  |  |  | 주제어건물/ELEVATION-NORTH | 2009-01-01 |  | 2008-04-15 |  | 2009-01-15 |  | 2008-04-29 |  | 2009-01-31 |  | 2009-02-12 | 현엔영월 제09-136호 | 2009-02-15 |  | 2009-04-20 | 62302-54050006-497 | 2009-02-28 |  | 2009-07-14 | 현엔영월 제09-675호 | 2009-08-31 |  | 2009-08-31 | [50 empty] | 62302-54050006-497@2009-04-20@Rev-A@Sts- | 현엔영월 제10-233호@2010-06-01@Rev-2@Pur-C | 1-85500-UA-112-108
4 | 1-85500-UA-112-110 | AR | A | 14A30 | 1 |  | A1 |  | 2 | 1 |  |  |  | 주제어건물/MAIN SECTION | 2009-01-01 |  | 2008-04-15 |  | 2009-01-15 |  | 2008-04-29 |  | 2009-01-31 |  | 2009-02-12 | 현엔영월 제09-136호 | 2009-02-15 |  | 2009-04-20 | 62302-54050006-497 | 2009-02-28 |  | 2009-07-14 | 현엔영월 제09-675호 | 2009-08-31 |  | 2009-08-31 | [50 empty] | 62302-54050006-497@2009-04-20@Rev-A@Sts- | 현엔영월 제09-1143호@2009-11-30@Rev-1@Pur-C | 1-85500-UA-112-110
5 | 1-85500-UA-112-158 | AR | A | 14A30 | 2 |  | A1 |  | 2 | 1 |  |  |  | 주제어건물/DOOR & WINDOW SCHEDULE | 2009-01-01 |  | 2008-04-15 |  | 2009-01-15 |  | 2008-04-29 |  | 2009-01-31 |  | 2009-02-12 | 현엔영월 제09-136호 | 2009-02-15 |  | 2009-04-20 | 62302-54050006-497 | 2009-02-28 |  | 2009-07-14 | 현엔영월 제09-675호 | 2009-08-31 |  | 2009-08-31 | [50 empty] | 62302-54050006-497@2009-04-20@Rev-A@Sts- | 현엔영월 제09-1143호@2009-11-30@Rev-2@Pur-C | 1-85500-UA-112-158
6 | 1-85500-UA-113-209 | AR | A | 14A30 | 2 |  | A1 |  | 2 | 1 |  |  |  | 주제어건물/FRAMING ELEVATION | 2008-07-01 |  | 2008-02-29 |  | 2008-07-15 |  | 2008-04-29 |  | 2008-08-01 |  | 2008-07-03 | 현엔영월 제08-220호 | 2008-08-15 |  | 2008-09-02 | 62302-54050011-1114호 | 2008-08-31 |  | 2008-09-25 | 현엔영월 제08-415호 | 2009-08-31 |  | 2009-10-01 | [51 empty] | 현엔영월 제09-674호@2009-06-30@Rev-2@Pur-C | 1-85500-UA-113-209
7 | 1-85500-UA-113-217 | AR | A | 14A30 | 1 |  | A1 |  | 2 | 1 |  |  |  | 주제어건물/FOUNDATION RE-BAR DETAIL | 2008-07-01 |  | 2008-02-29 |  | 2008-07-15 |  | 2008-04-29 |  | 2008-08-01 |  | 2008-08-26 | 현엔영월 제08-341호 | 2008-08-15 |  | 2008-09-02 | 62302-54050011-1114호 | 2008-08-31 |  | 2008-09-25 | 현엔영월 제08-415호 | 2009-08-31 |  | 2009-08-31 | [51 empty] | 현엔영월 제09-515호@2009-05-11@Rev-1@Pur-C | 1-85500-UA-113-217
8 | 1-85500-UA-113-232 | AR | A | 14A30 | 2 |  | A1 |  | 2 | 1 |  |  |  | 주제어건물/GIRDER & BEAM LIST | 2008-07-01 |  | 2008-07-01 |  | 2008-07-15 |  | 2008-07-15 |  | 2008-11-30 |  | 2008-11-12 | 현엔영월 제08-594호 | 2008-12-08 |  | 2008-12-02 | 62302-54050011-1572호 | 2008-12-15 |  | 2008-12-03 | 현엔영월 제08-661호 | 2009-08-31 |  | 2009-08-31 | [50 empty] | 62302-54050011-1572@2008-12-02@Rev-A@Sts- | 현엔영월 제09-674호@2009-06-30@Rev-2@Pur-C | 1-85500-UA-113-232