## 안마도
[ 안마도 220MW 해상풍력 ]
Date | 공종 | 구분 | 담당 | 기한 | 비고
| 사업개요 | 1. 사업명 : 전남 안마도 해상풍력 발전사업 2. 용량 : 224MW (8MW x 28기) 3. 사업부지 : 전남 영광군 안마도 서측 해상 4. 총투자비 : 1.6조원 (EPC 약 1.4조원) 5. 발주처 : SPC(안마해상풍력㈜)
| 사업일정 | 6. 사업추진현황 - ’17.09 사업주 MOU 체결 및 SPC 설립 - ’17.10 육상 LiDAR (풍황계측기) 설치 - ’18.06 정부 R&D 과제 선정 및 협약체결 - ’19.04 전기사업허가 승인 - ’19.05 해상 LiDAR 설치 - ’19.08 해양물리 및 시추조사 용역 완료 (지층탐사, 시추조사) - ’20.09 EPC Indicative Proposal 제출 - ’20.10 정부 R&D 과제 완료 - ’21.02 당사 내부 1차투자심의 통과 (개념설계용역비 10억원 승인) 7. 향후일정 - ’21.1Q 개념설계 착수 (~’21.08) - ’21.09 기본설계 착수 (~’21.12) - ’22.1Q EPC 계약체결 - ’22.2Q 착공
2021.04.05 |  | ▶ARUP 기술 계약서 검토 요청 |  | 2021.04.06
2022.02 | 안마도 공사스케줄(Draft_220125r) | 1) 개념설계 2단계 계약 : ~2022.03 - ARUP Proposal 검토 - 1단계 220MW + 2단계 300MW 2) 1 & 2 단계 통합 Feed 설계 : 2022.03~2022.11 3) 실시설계 : 2022.11 ~ 2023.11 - 내부 설계 및 현장 지원 30 MM
2022.03.02 | [내부 인수인계 회의 22.03.02]
| 업무진행 현황 및 수행분야 | - 업무진행 현황: 개념설계(Phase 1&2), 현재 진행 중 -> FEED 설계 -> 상세설계 - 업무수행 분야: 기계, 전기, 토목 / 건축, 소방, 공조, 계장 - 사업부 건축담당 : 박건원 책임 (신재생사업 1팀)
| <Phase 1: 224MW Offshore Wind Farm> | Substation Type - Phase 1: Offshore Type 검토 - Phase 2: Onshore Type 변경 적용 예정 (성과품 반영 확인)
| 1. Building List | - Building List_Rev.1_Seq.3_220217 (첨부자료 참조) |  |  | 첨부 1.
| 2. Building Finish | - 이전 입찰 시 작용한 마감사양 적용 (BOQ_Rev.A_Seq.1_200312 기준 / 특이사항 없음)
| 3. BM | - Building BOQ_Rev.1_Seq.3_220217 (첨부자료 참조) |  |  | 첨부 2.
| 4. 물량 산출 근거 | - 154kV/66kV GIS Building, Monitoring & GIS Control Building, 154kV Switching Station : 전기분야 요청사항 반영 / ABOQ, Excel Sheet 물량산출 - Monitoring House, Warehouse: 기술자문사(ARUP) 성과품 반영 / ABOQ, Excel Sheet 물량산출 |  |  | 첨부 2.
| 5. 도면 | - 타분야 (전기) 요청사항 및 기술자문사(ARUP) 성과품 반영하여 도면작성 (첨부자료 참조) |  |  | 첨부 2.
| 6. ARUP 성과품 - Comment & Reply | - 기술자문사 (ARUP) 성과품 건축관련 검토 1) 주요 검토 성과품: Monitoring House, Substation 관련 도서 2) 이외 성과품: 건축관련 사항 유무 확인 - Update : Review Results of Deliverable List |  |  | 첨부 3. (Phase 1.)
| 7. 물량 검토보고서 | - 육상변전소 기준 (Base), 사업부 수정 요청사항 반영하여 최종 송부 (22.02.17)  1) Monitoring House, Warehouse (목포신항/O&M Port -> 영광군 변경 적용 / 기존 영광군 물량 삭제)  2) Option 물량 삭제 (해상변전소 기준 산출 물량) - Foundation Type 1) 죽도 위치 건물 : Non-Pile Shallow Foundation 2) 영광군 위치 건물 : Pile Foundation (PHC D400, 30m) |  |  | 첨부 4.
| 8. Proposal | - Indicative Proposal 작성 (2022.02.08, 사업부 최종 수정 / 물량검토보고서 수정사항과 동일) |  |  | 첨부 5.
| 9. 향후 일정 | 1. <Phase 2: 304MW Offshore Wind Farm> : 수행 예정 (3월 말 완료 계획) 2. <Phase 1&2 FEED: 528MW Offshore Wind Farm> : 수행 예정 (4월 중 예상)
2022.03.03 | 전기 Anma-do OWF [Phase 2] - Clarification on Monitoring House Location Selection Report | [ARUP 질의 사항] According to the scope of works, this report will be a continuation of Phase 1 based on new information received from the Client. As of today, we have justreceived one clarification from HEC that Yeonggwang Monitoring House will be the Major Monitoring House, and Anmado Monitoring House will be the Minor Monitoring House. To facilitate our works on this report, please could HEC provide any available informationrelated to the preferred location, and purpose of each monitoring house? -> HEC : Please see below the location and purpose of major and minor monitoring house. 1. Major monitoring house: located just next to the yeonggwang switching station, for overall monitoring & control, operation for the ANMA phase1&2. (*Considering LTSA with the WTG supplier (20 years), we expect they will provide the necessary CTV or SOV to supply andtransport repair parts and maintenance personnel.) 2. Minor monitoring house : New jetty for CTV location is expected to south of ANMA island(refer to below photo), but monitoring house location is notdetermined yet.(JUKDO or ANMA island) For routine/light O&M for the ANMA phase1&2 | 전기팀 김종성 책임 | 송석 책임 E-Mail 회신
2022.02.25 | [안마해상풍력] WTG 배치관련 변경사항 안내 | [ARUP 질의 사항 02.25] Please confirm that the two triangle areas(green area) have been removed from consideration. This will make the second and third rows denser. • HEC 회신 : According to therecent maritime traffic safety diagnosis, the two triangle areas should be deleted as it was requested to be 3.6 km apart from Anma Island according to the analysis result of the ship's track map near Anma Island. 2. For the SGRE layout, please confirm if we should aim at 230MW (23 no. of 10MW turbines) for phase 1 and 300MW (30 no. of 10MW turbines) for phase 2 • HEC 회신 : 230MW (23 no. of 10MW turbines) for phase 1 and 310MW(31no. of 10MW turbines) for phase 2 |  | 송석 책임 E-Mail 회신
2022.03.03 | [안마해상풍력] WTG 배치관련 변경사항 안내 | [ARUP 메일 03.03] Regarding the SGRE layout, the power curve we received in phase 1 is a 10.5MW model. Please can you confirm if we should aim at 567MW instead of 540MW for 54 nos. of turbine in total. |  | 송석 책임 E-Mail 회신